2018 FOURTH QUARTER/FULL YEAR BUDGET APPRAISAL

BY

MONITORING & EVALUATION DEPARTMENT,

MINISTRY OF ECONOMIC PLANNING & BUDGET

January, 2019

TABLE OF CONTENTS

Title Page…………………………….........................................................1

Table of Contents…………………………………………………………………………2

List of Tables……………….………………………………………………………………3

List of Figures………………………………………………………………………………4

Preface………………………………………………………………………..................6

Executive Summary………………………………………………………………………8

Chapter One:	Introduction………………………………………………………10

Chapter Two: 	Revenue Profile and Analysis……………………………...14

Chapter Three: 	Expenditure Profile and Analysis………………………....25

Chapter Four: 	Status of Capital Projects Awarded in 2018

Through State Tenders’ Board………………..…………..50

Chapter Five: 	Observations, Recommendations and Conclusions…55

Appendix..………………………………………………………………………………….59

LIST OF TABLES

Table 2.1: Summary of 2018 Revenue on Quarterly Basis.................14

Tabl2 2.2: Summary of Revenue Receipts in 2018……...........…………16

Table 2.3: Details of Full Year Revenue Receipts from Federation

Account…………………………………………………………..………..21

Table 2.4: Details of Full Year Independent Revenue….………….………22

Table 2.5: Details of Full Year Revenue Receipts from

Other Revenue Sources…………………………………………..….23

Table 3.1: Summary of 2018 Quarterly Expenditures.....……….………..25

Table 3.2: Summary of 2018 Full Year Expenditures....…………………..27

Table 3.3: Details of Quarterly Recurrent Expenditure Components….33

Table 3.4: Details of Full Year Recurrent Expenditure Components…..35

Table 3.5: Details of Quarterly Personnel Cost……….….…………………..38

Table 3.6: Summary of Full Year Subvention/Grants to Parastatals…..41

Table 3.7: Details of Full Year Consolidated Revenue

Funds Charges (CRFC)..……………………………………………….43

Table 3.8: Full Year Sectoral Recurrent Expenditure Details...……….…45

Table 3.9: Details of Full Year Statutory Transfers...……………………….47

Table 3.10: Full Year Sectoral Capital Expenditure Details….…………...48

Table 4.1: Summary of Projects Awarded through STB in 2018….…….51

Table 4.2: Status of  UBEC/SUBEB Projects……………….......................52

Table 4.3: Summary of Projects executed by OSOPADEC...................53

Table 4.4: Status of OSOPADEC Projects...............................………....54

LIST OF FIGURES

Figure 2.1: Bar Chart Showing Quarterly Revenue Performance.…….15

Figure 2.2: Bar Chart Showing Full Year Revenue Performance.……..17

Figure 2.3: Bar Chart Showing Quarterly Performance of

Revenue Categories ………………………………………………….18

Figure 2.4: Bar Chart Showing Full Year Performance of

Revenue Categories ………………………………………………….19

Figure 2.5: Pie Chart Showing Share of Full Year

Actual Revenue Components……………………………………...20

Figure 2.6: Bar Chart Showing Full Year Performance of

Revenue Receipts from Federation Account………………….21

Figure 2.7: Bar Chart Showing Full Year Independent

Revenue Performance..………………….………………………..23

Figure 2.8: Bar Chart Showing Full Year Performance of Revenue

Receipts from Other Revenue Sources……………………...24

Figure 3.1: Bar Chart Showing Quarterly Total Expenditure

Performance……………………………………………………………26

Figure 3.2: Bar Chart Showing Full Year Total Expenditure

Performance……………………………………………………………28

Figure 3.3: Bar Chart Showing Quarterly Performance of

Expenditure Classifications………………………………………..29

Figure 3.4: Bar Chart Showing Full Year Performance of

Expenditure Classifications………………………………………..31

Figure 3.5: Pie Chart Showing Share of Full Year Actual

Expenditure Performance………………………………………….32

Figure 3.6: Bar Chart Showing Quarterly Recurrent Expenditure

Components…………………………………………………………….34

Figure 3.7: Bar Chart Showing Full Year Recurrent Expenditure

Components…………………………………………………………….35

Figure 3.8: Pie Chart Showing Share of Full Year Actual

Recurrent Expenditure Components…………….…………….36

Figure 3.9: Bar Chart Showing Full Year Personnel Cost….……………37

Figure 3.10: Bar Chart Showing Full Year Overhead Cost………………39

Figure 3.11: Bar Chart Showing Full Year Special Programme.………40

Figure 3.12: Bar Chart Showing Full Year Subventions to

Institutions and Agencies……………………………………….42

Figure 3.13: Bar Chart Showing Full Year Consolidated

Revenue Fund Charges (CRFC)………………………………43

Figure 3.14: Bar Chart Showing Full Year Grants/Loan……….……….44

Figure 3.15: Bar Chart Showing Full Year Sectoral

Recurrent Expenditure………………………………………….46

Figure 3.16: Bar Chart Showing Full Year Statutory Transfer………47

Figure 3.17: Bar Chart Showing Full Year Sectoral

Capital Expenditure…………………………………..…………..49

Figure 4.1: Bar Chart Showing Status of SUBEB Projects.......……...52

PREFACE

Budget is an estimate of costs, revenues, and resources over a specified period, reflecting a reading of future financial conditions and goals. It is compiled and re-evaluated on a periodic basis; hence, budget performance report is an essential part of the State accountability mechanism stipulated in the Ondo State Fiscal Responsibility Law, 2017.

The year 2018 budget was the second budget prepared under the Arakunrin Oluwarotimi Odunayo Akeredolu-led Administration to implement his five cardinal programmes for the development of Ondo State.

This Appraisal, therefore, evaluates the implementation of the 2018 Fourth Quarter and Full Year estimates with respect to all disbursements and assesses the realisation of all fiscal targets during the periods under review. Also, it identifies gaps, provides lessons, highlights significant accomplishments, and offers recommendations for improvement.

The publication of this report is principally in fulfillment of Section 39(3) of the Ondo State Fiscal Responsibility Law, (FRL), 2017. We therefore, urge the general public and readers of this Report to maintain active interest in tracking progress towards attainment of Government’s goals and objectives especially government’s management of public resources. We look forward to your active participation in the entire budget process.

Department of Monitoring and Evaluation,

Ministry of Economic Planning and Budget,

Alagbaka, Akure.

EXECUTIVE SUMMARY

The 2018 Budget has the theme “Budget of Progress” and is closely linked to the Strategic Development and Policy Implementation plan document tagged the Blueprint to Progress of this administration. The Budget was therefore designed to demonstrate Government’s commitment to create a more diversified, sustainable and inclusive economy. It has the objective to open up the hidden potentials of our people, communities and natural endowments across every part of the State.

The State approved a total budget of N181.425 billion in 2018 and the total amount was also maintained when the budget was re-ordered. The budget is therefore broken into N13.600 billion for Debt Repayment (Principal), N8.308 billion for Statutory Transfers, N88.654 billion for Recurrent Expenditure and N70.863 billion for Capital Expenditure, with a corresponding total of N181.425 billion as envisaged revenue for the year.

The revenue side of the budget for the fourth quarter recorded total receipts of N46.337 billion against proposed target of N45.378 billion while the full year actual revenue was N113.947 billion against proposed targets of N181.426 billion for the year. The breakdown of these receipts for the fourth quarter and full year showed Internally Generated Revenue (IGR) as N10.327 billion and N24.790 billion respectively. Revenue from the Federation Account recorded N32.273 billion for fourth quarter and N85.380 billion for full year while revenue from Other sources was N5.524 billion for fourth quarter and N9.158 billion for full year. The overall revenue for the State was N119.328 billion inclusive of revenue from Revenue Retaining Agencies (RRA), representing 65.8% performance while 62.8% was the revenue performance without RRA.

On the other hand, the total actual expenditure for the fourth quarter was N35.360 billion against the proposed estimates of N45.356 billion while the full year actual expenditure was N110.686 billion against the budget estimates of N181.424 billion for the year. These figures depicted overall performance level of 78% for fourth quarter and 61% for full year. The breakdown of the figures for the Fourth Quarter showed that the actual recurrent expenditure was N20.001 billion, representing 90.2%, Debt Repayment N1.545 billion, representing 45.5%, Statutory Transfer N1.625 billion, representing 78.2%, while the actual capital expenditure stood at N12.188 billion, representing 68.8% performance.

Similarly, the breakdown of the figures for the full year showed that the actual recurrent expenditure was N71.273 billion, representing 80.4%, Debt Repayment N7.221 billion, representing 53.0%, Statutory Transfer N5.872 billion, representing 70.7%, while the actual capital expenditure stood at N26.329 billion, representing 37.2% performance for the year.

Further breakdown and analysis of the 2018 budget implementation appraisal is structured in chapters. Chapter one discusses the introduction, objectives and policy thrust of the 2018 budget. Details of revenue profile and analysis for the fourth quarter and full year are contained in chapter two. Chapter three focuses on the expenditure profile and analysis, Chapter four covers status of capital projects awarded in 2018 through the State Tenders’ Board while chapter five highlights the observations, recommendations and conclusion.

CHAPTER ONE

1.1	INTRODUCTION

The 2018 Budget was closely linked with the Strategic Development and Policy Implementation Plan document tagged the Blueprint to Progress of this administration and was designed to focus on rebuilding the State’s economy through prioritised investment on infrastructural facilities and agriculture-related activities. It also aimed at strengthening partnership between public and private sector as well as Development Partners to leverage and catalyze resources for growth.

The 2018 Full Year Budget Appraisal Report  provides insight into the Ondo State Government’s Budget Implementation and Performance so far. It includes an overview of budget implementation activities, a brief analysis of the macroeconomic context within which the 2018 Budget was executed, and an analysis of the Government’s revenue receipts and expenditure in the year under review.

1.2	OBJECTIVES AND POLICY THRUST OF 2018 BUDGET

The 2018 Budget was hinged on the following objectives:

- Intensify efforts on Independent Revenue (IR) initiatives by increasing IR by 100%;

- Massive infrastructural development;

- Wealth creation through empowerment of youths, artisans, farmers and market women;

- Enhancement of agriculture-related activities; and

- Enhancement of community development through improved collaboration with communities.

1.3	STRATEGIES FOR ACHIEVING OBJECTIVES OF 2018 	BUDGET

The Strategies to achieve the objectives of the 2018 Budget among others are:

- Activation of IPSAS revenue codes for easy lodgement of revenue;

- Engagement of Revenue Consultants to help drive Independent Revenue Generation;

- Resuscitation of decaying infrastructural facilities;

- Provision of farm inputs and improved seedlings to farmers to boost food production;

- Deployment of ICT to empower and create wealth for the youths and artisans;

- Collaboration with relevant Federal Agencies and Development partners to support State initiatives; and

- Enhancing accessibility to semi-urban and rural areas through opening-up of rural feeder roads.

1.4	METHODOLOGY

The Methodology adopted in the production of this report draws from a number of inter-related approaches. The aim is to offer representative information that accurately provides necessary context for verifying the quality, efficiency and effectiveness of the Government’s programmes and their attendant progress towards implementation, to reflect the increased demand for transparency and accountability in Government. A combination of desk review and data collection and analysis were adopted in order to justify budgetary resource allocation. Data were collected through the administration of uniform templates that were consistent with the M&E Framework. These primary levels data were collected from the MEDAs for further data quality, assessment, analysis and interpretation.

1.5	LIMITATIONS

Few limitations were encountered during the preparation of the report that might have affected timely reporting of the appraisal. These include:

- Submission of Returns - Usually, several MEDAs find it difficult to meet the deadline to which they are expected to submit their returns. This hereby prolongs unneccessarily the stipulated time the report should be ready.

- Validation of Data – At times, when returns are rendered by MEDAs, there are contradictions in the data with relevant Government Institutions, so the Department repeatedly validates the data from Board of Internal Revenue (BIR), Office of Accountant General (OAG), and Debt Management Department (DMD).

- Untimely Release of Fund – Prompt release of fund for this exercise goes a long way to ensure the Department produce the report within the stipulated timeline.

CHAPTER TWO

2.1	REVENUE PROFILE AND ANALYSIS

The table below shows the details of the Revenue inflow to the State from all sources in each quarter for the fiscal year 2018. Table 2.1  classifies the revenue receipts to the State into three categories. These are: Revenue from the Federation Account, Independent Revenue [Internally Generated Revenue, (IGR)] and Revenue from Other Sources.

|  | Revenue Sources | Quarterly Target | 1st Quarter Actual | 2nd Quarter Actual | 3rd Quarter Actual | 4th Quarter Actual |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | (N’B) | (N’B) | (N’B) | (N’B) | (N’B) |
| (A) | Revenue from Federation Account |  |  |  |  |  |
| i. | Statutory Allocation | 6.338 | 9.444 | 9.556 | 10.265 | 9.837 |
| ii. | Value Added Tax | 3.000 | 2.819 | 2.757 | 2.960 | 2.883 |
| iii. | Mineral Derivation Fund | 3.884 | 4.874 | 4.418 | 4.167 | 4.727 |
| iv. | Budget Support Facility Loan | 2.731 | 0.004 | 0.000 | 0.000 | 0.000 |
| v. | Paris Club Refund | 3.289 | 0.000 | 0.000 | 0.000 | 14.122 |
| vi. | Petroleum Profit Tax/Excess Crude | 0.920 | 0.000 | 0.108 | 0.125 | 0.010 |
| vii. | Refund on Federal Roads | 2.500 | 0.000 | 0.000 | 0.000 | 0.000 |
| vii. | Exchange Gain/Forex Stabilization Account | 1.532 | 0.324 | 0.635 | 0.651 | 0.694 |
|  | Sub-total | 24.194 | 17.465 | 17.474 | 18.168 | 32.273 |
| (B) | Independent Revenue |  |  |  |  |  |
| i. | BIR | 3.413 | 2.420 | 2.882 | 2.617 | 3.801 |
| ii. | MEDAs | 1.842 | 0.633 | 0.812 | 1.505 | 4.739 |
| iii. | Revenue Retaining Agencies (RRA) | 0.000 | 0.557 | 2.114 | 0.923 | 1.787 |
|  | Sub-total | 5.255 | 3.610 | 5.808 | 5.045 | 10.327 |
| (C) | Other Revenue Sources |  |  |  |  |  |
| i. | Rollover Fund (Fixed Deposit Recall) | 3.375 | 0.600 | 1.720 | 0.950 | 1.660 |
| ii. | Credit from Development Partners | 3.187 | 0.104 | 0.100 | 0.151 | 1.802 |
| iii. | Grants from donor agencies | 1.569 | 0.000 | 0.000 | 0.000 | 2.062 |
| iv. | Loans/Leases | 7.798 | 0.000 | 0.000 | 0.000 | 0.000 |
| v. | Excess Bank Charges | 0.000 | 0.004 | 0.005 | 0.000 | 0.000 |
|  | Sub-total | 15.929 | 0.708 | 1.825 | 1.101 | 5.524 |
|  | Total | 45.378 | 21.783 | 25.107 | 24.314 | 48.124 |
|  | Less (RRA) |  | 0.557 | 2.114 | 0.923 | 1.787 |
|  | GRAND TOTAL | 45.378 | 21.226 | 22.993 | 23.391 | 46.337 |

Table 2.1: Summary of 2018 Revenue on Quarterly Basis

Source: Office of Accountant General, Board of Internal Revenue & Other MEDAs

Figure 2.1: Bar Chart Showing Quarterly Revenue Performance

Figure 2.1 above compares the total actual revenue for the four quarters of 2018 with the proposed quarter revenue target. It shows that the actual total revenue for the four quarters are N21.226 billion, N22.993 billion, N23.391 billion and N46.337 billion respectively against the proposed quarterly revenue targets of N45.378 billion, representing 46.8%, 50.7% 51.6% and 102.1% performance levels.

Table 2.2:	 Summary of Revenue in 2018

|  | Revenue Sources | 2018 Approved Targets | 2018 Actual | Performance (%) |
| --- | --- | --- | --- | --- |
|  |  | (N’B) | (N’B) |  |
| (A) | Revenue from Federation Account |  |  |  |
| i. | Statutory Allocation | 25.352 | 39.102 | 154.24 |
| ii. | Value Added Tax | 12.000 | 11.419 | 95.16 |
| iii. | Mineral Derivation Fund | 15.536 | 18.186 | 117.06 |
| iv. | Budget Support Facility Loan | 10.925 | 0.004 | 0.04 |
| v. | Paris Club Refund | 13.156 | 14.122 | 107.34 |
| vi. | Petroleum Profit Tax/Excess Crude | 3.683 | 0.243 | 6.60 |
| vii. | Refund on Federal Roads | 10.000 | 0.000 | 0.00 |
| viii. | Exchange Gain/Forex Stabilization Account | 6.126 | 2.304 | 37.61 |
|  | Sub-total | 96.778 | 85.380 | 88.22 |
| (B) | Independent Revenue |  |  |  |
| i. | BIR | 13.650 | 11.720 | 85.86 |
| ii. | MEDAs | 7.276 | 7.689 | 105.68 |
| iii. | Revenue Retaining Agencies (RRA) |  | 5.381 |  |
|  | Sub-total | 20.926 | 24.790 | 118.47 |
| (C) | Other Revenue Sources |  |  |  |
| i. | Rollover Fund (Fixed Deposit Recall) | 13.500 | 4.930 | 36.52 |
| ii. | Credit from Development Partners | 12.748 | 2.157 | 16.92 |
| iii. | Grants from donor agencies | 6.279 | 2.062 | 32.84 |
| iv. | Loans/Leases | 31.195 | 0.000 | 0.00 |
| v. | Excess Bank Charges |  | 0.009 | 0.00 |
|  | Sub-total | 63.722 | 9.158 | 14.37 |
|  | Total | 181.426 | 119.328 | 65.77 |
|  | Less (RRA) |  | 5.381 |  |
|  | GRAND TOTAL | 181.426 | 113.947 | 62.81 |

Source: Office of Accountant General, Board of Internal Revenue & Other MEDAs

Table 2.2 shows aggregate revenue receipt from all sources in the 2018 fiscal year. A total of N113.947 billion was realised by the State which represents 62.8% performance level. When N5.381 billion actual revenue generated by the Revenue Retaining Agencies were added to this figure, it increased the total revenue of the State in 2018 to N119.328 billion, representing 65.8% performance.

Figure 2.2: Bar Chart Showing Full Year Revenue Performance

Figure 2.3: Bar Chart Showing Quarterly Revenue Categories

Figure 2.3 further illustrates the analysis of revenue performance of the three categories of Revenue Sources to the State. Comparing each revenue category targets with the actual receipt for the four quarters. The chart indicates that actual revenue and performance from the Federation Account for the First quarter was N17.465 billion  (72.2%), Second quarter  N17.474 billion (72.2%), Third quarter N18.168 billion (75.1%) and Fourth quarter N32.273 billion (133.4%).

In similar manner, a target of N5.255 billion was set for Independent Revenue for each quarter of year 2018 while the actual revenues generated were N3.053 billion (58.1%), N3.694 billion (70.3%), N4.122 billion (78.4%) and N8.540 billion (162.5%) respectively for the four quarters.

Following the same trend, revenue from Other Sources for the four quarters recorded actuals and performances of N0.708 billion (4.4%), N1.825 billion (11.5%) , N1.101 billion (6.9%) and N5.524 billion (34.7%) respectively against the quarterly target of N15.929 billion.

Figure 2.4: Bar Chart Showing Full Year Revenue Categories

Figure 2.4 depicts the full year performance of Revenue Categories for the year 2018. At the end of the year, Federation Account recorded an actual and performance of N85.380 billion (88.2%), Independent Revenue N24.790 billion (118.5%) and Other Revenue Sources N9.159 billion (14.4%).

Figure 2.5: Pie Chart Showing Share of Full Year Actual

Revenue Performance

Figure 2.5 shows the proportion of actual revenue receipts from the three Revenue Sources for the year 2018. Out of the total actual revenue of N113.947 billion realised for the year, Independent Revenue accounted for 17% (less RRA), revenue from Other Sources 8% and Federation Account  75%.

Table 2.3: Details of Full Year Revenue from Federation Account

|  | Revenue Sources | 2018 Approved Targets | 2018 Actual | Performance (%) |
| --- | --- | --- | --- | --- |
|  |  | (N’B) | (N’B) |  |
|  | Revenue from Federation Account |  |  |  |
| i. | Statutory Allocation | 25.352 | 39.102 | 154.24 |
| ii. | Value Added Tax | 12.000 | 11.419 | 95.16 |
| iii. | Mineral Derivation Fund | 15.536 | 18.186 | 117.06 |
| iv. | Budget Support Facility Loan | 10.925 | 0.004 | 0.04 |
| v. | Paris Club Refund | 13.156 | 14.122 | 107.34 |
| vi. | Petroleum Profit Tax/Excess Crude | 3.683 | 0.243 | 6.60 |
| vii. | Refund on Federal Roads | 10.000 | 0.000 | 0.00 |
| viii. | Exchange Gain/Forex Stabilization Account | 6.126 | 2.304 | 37.61 |
|  | Sub-total | 96.778 | 85.380 | 88.22 |

Source: Office of Accountant General

Figure 2.6: Bar Chart Showing Full Year Revenue from

Federation  Account

Table 2.3 shows a breakdown of the receipt from the Federation Account for year 2018. Performance of Statutory Allocation was 154.2%, Value Added Tax 95.2%, Mineral Derivation Fund 117.1%, Budget Support Facility Loan 0.04%, Paris Club Refund 107.3%, Petroleum Profit Tax/Excess Crude 6.6% and Exchange gain/Forex and Stabilization Account 37.6%.

Table 2.4: Details of Full Year Independent Revenue

|  | Revenue Sources | 2018 Approved Targets | 2018 Actual | Performance (%) |
| --- | --- | --- | --- | --- |
|  | Independent Revenue |  |  |  |
| i. | BIR | 13.65 | 11.720 | 85.86 |
| ii. | MEDAs | 7.276 | 7.689 | 105.68 |
|  | Sub-total | 20.926 | 19.409 | 92.75 |
| iii. | Revenue Retaining Agencies (RRA) |  | 5.381 |  |
|  | Total | 20.926 | 24.79 | 118.47 |

Source: Board of Internal Revenue

Table 2.4 shows the breakdown of independent revenue performance. BIR generated N11.720 billion, representing 85.9% performance while MEDAs generated N7.689 billion, representing 105.7%. The total IGR without RRA was N19.409 billion, representing           92.8% while with RRA, it was 118.5%.

Figure 2.7: Bar Chart showing Full Year Independent Revenue

Table 2.5: Details of Full Year Revenue Receipts from Other Sources

|  | Revenue Sources | 2018 Approved Targets | 2018 Actual | Performance (%) |
| --- | --- | --- | --- | --- |
|  | Other Revenue Sources |  |  |  |
| i. | Rollover Fund (Fixed Deposit Recall) | 13.500 | 4.930 | 36.52 |
| ii. | Credit from Development Partners | 12.748 | 2.157 | 16.92 |
| iii. | Grants from donor agencies | 6.279 | 2.062 | 32.84 |
| iv. | Loans/Leases | 31.195 | 0.000 | 0.00 |
| v. | Excess Bank Charges |  | 0.009 | 0.00 |
|  | Sub-total | 63.722 | 9.158 | 14.37 |

Source: Office of Accountant General, Board of Internal Revenue & Other MEDAs

Table 2.5 compares the target of components of Revenue from Other Sources with actuals for the year 2018. It shows that Rollover Fund target was N13.500 billion against actual of N4.930 billion performing at 36.5%, Credit from Development Partners target was N12.748 billion against actual of N2.157 billion, performing at 16.9%, Grants from Donor Agencies target was N6.279 billion against actual of N2.062 billion performing at 32.8%. Loans/Leases did not record any inflow for the year. The total sum of revenue receipt from Other Sources was N9.158 billion performing at 14.4%.

Figure 2.8: Bar Chart Showing Full Year Revenue Receipts from Other Sources

CHAPTER THREE

  - EXPENDITURE PROFILE AND ANALYSIS

Table 3.1 shows the details of the quarterly expenditures for the year 2018.

Table 3.1: Summary of 2018 Quarterly Expenditure

| S/N | EXPENDITURE DETAILS | QUARTERLY ESTIMATES N | FIRST QUARTER ACTUAL N | SECOND QUARTER ACTUAL N | THIRD QUARTER ACTUAL N | FOURTH QUARTER ACTUAL N |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | PERSONNEL COST | 10,005,920,769.81 | 7,922,604,467.29 | 8,629,192,940.34 | 8,489,554,539.75 | 8,357,644,680.92 |
| 2 | OVERHEAD COST | 1,125,754,875.00 | 781,682,376.65 | 1,001,709,911.30 | 893,618,741.49 | 819,581,625.67 |
| 3 | SPECIAL PROGRAMME | 4,180,334,489.71 | 2,035,929,337.84 | 2,200,655,856.46 | 3,165,143,100.95 | 4,048,073,172.44 |
| 4 | GRANTS TO PARASTATALS/SUBVENTION | 2,247,609,921.52 | 919,742,037.50 | 1,244,867,337.50 | 2,458,784,584.00 | 2,880,646,154.00 |
| 5 | CONSOLIDATED REVENUE FUND CHARGE | 4,566,417,250.00 | 3,735,999,309.07 | 3,592,314,385.46 | 4,103,021,833.73 | 3,859,278,372.52 |
| 6 | GRANTS/LOANS | 37,500,000.00 | 35,465,600.00 | 26,599,200.00 | 35,465,600.00 | 36,215,600.00 |
| A | TOTAL RECURRENT EXPENDITURE | 22,163,537,306.04 | 15,431,423,128.35 | 16,695,339,631.06 | 19,145,588,399.92 | 20,001,439,605.55 |
|  | DEBT SERVICE | 3,399,969,521.16 | 2,580,733,868.32 | 1,541,661,485.94 | 1,543,500,745.67 | 1,545,390,242.10 |
| B | DEBT REPAYMENT (PRINCIPAL) | 3,399,969,521.16 | 2,580,733,868.32 | 1,541,661,485.94 | 1,543,500,745.67 | 1,545,390,242.10 |
|  | STATUTORY TRANSFERS |  |  |  |  |  |
| 1 | TRANSFER TO LOCAL GOVERNMENT JOINT ACCOUNT (10%) | 523,341,169.58 | 127,868,122.86 | 133,982,328.17 | 145,711,156.69 | 145,711,156.69 |
| 2 | TRANSFER TO OSOPADEC | 1,553,659,200.00 | 639,125,944.35 | 1,721,554,600.17 | 1,479,147,014.34 | 1,479,147,014.34 |
| C | TOTAL STATUTORY TRANSFER | 2,077,000,369.58 | 766,994,067.21 | 1,855,536,928.34 | 1,624,858,171.03 | 1,624,858,171.03 |
|  | CAPITAL EXPENDITURE |  |  |  |  |  |
| 1 | MEDAs/INSTITUTIONS | 17,715,627,873.98 | 2,754,078,937.35 | 5,032,575,336.34 | 6,353,610,448.44 | 12,188,422,513.70 |
| D | TOTAL CAPITAL EXPENDITURE | 17,715,627,873.98 | 2,754,078,937.35 | 5,032,575,336.34 | 6,353,610,448.44 | 12,188,422,513.70 |
|  | GRAND TOTAL | 45,356,135,070.75 | 21,533,230,001.23 | 25,125,113,381.68 | 28,667,557,765.06 | 35,360,110,532.38 |

Source: Office of Accountant General and other MEDAs, Ondo State

Figure 3.1: Bar Chart Showing Quarterly Total Expenditure Performance

Figure 3.1 compares the total actual expenditure for the four quarters of year 2018 with the quarterly estimates. The total actual expenditure for the fourth quarter was N35.360 billion against the proposed estimates of N45.356 billion. This represents a 78.0% overall performance level for the quarter while the first quarter overall performance was 47.5%, second quarter 55.4% and 63.2% for the third quarter.

Table 3.2: Summary of 2018 Full Year Expenditure

| S/N | EXPENDITURE DETAILS | APPROVED ESTIMATES N | FULL YEAR ACTUAL N | PERFORMANCE LEVEL (%) |
| --- | --- | --- | --- | --- |
| 1 | PERSONNEL COST | 40,023,683,079.25 | 33,398,996,628.30 | 83.45 |
| 2 | OVERHEAD COST | 4,503,019,500.00 | 3,496,592,655.11 | 77.65 |
| 3 | SPECIAL PROGRAMME | 16,721,337,958.82 | 11,449,801,467.69 | 68.47 |
| 4 | GRANTS TO PARASTATALS/SUBVENTION | 8,990,439,686.07 | 7,504,040,113.00 | 83.47 |
| 5 | CONSOLIDATED REVENUE FUND CHARGE | 18,265,669,000.00 | 15,290,613,900.78 | 83.71 |
| 6 | GRANTS/LOANS | 150,000,000.00 | 133,746,000.00 | 89.16 |
| A | TOTAL RECURRENT EXPENDITURE | 88,654,149,224.14 | 71,273,790,764.88 | 80.40 |
|  | DEBT SERVICE | 13,599,878,084.63 | 7,211,286,342.03 | 53.02 |
| B | DEBT REPAYMENT (PRINCIPAL) | 13,599,878,084.63 | 7,211,286,342.03 | 53.02 |
|  | STATUTORY TRANSFERS |  |  |  |
| 1 | TRANSFER TO LOCAL GOVERNMENT JOINT ACCOUNT (10%) | 2,093,364,678.30 | 553,272,764.41 | 26.43 |
| 2 | TRANSFER TO OSOPADEC | 6,214,636,800.00 | 5,318,974,573.20 | 85.59 |
| C | TOTAL STATUTORY TRANSFER | 8,308,001,478.30 | 5,872,247,337.61 | 70.68 |
|  | CAPITAL EXPENDITURE |  | - |  |
| 1 | MEDAs/INSTITUTIONS | 70,862,511,495.93 | 26,328,687,235.83 | 37.15 |
| D | TOTAL CAPITAL EXPENDITURE | 70,862,511,495.93 | 26,328,687,235.83 | 37.15 |
|  | GRAND TOTAL (A+B+C+D) | 181,424,540,283.00 | 110,686,011,680.35 | 61.01 |

Source: Office of Accountant General and other MEDAs, Ondo State

Figure 3.2 compares the total actual expenditure for the full year with the approved estimates. The total actual expenditure was N110.686 billion against the approved estimates of N181.425 billion. This represents a 61.0% overall performance level for the year.

Figure 3.2: Bar Chart Showing Full Year Total Expenditure Performance

Figure 3.3: Bar Chart Showing Quarterly Performance of Expenditure Classifications

Figure 3.3 shows the performance of the expenditure classifications for the four quarters of the year 2018 against the quarterly estimates. The actual expenditures for the four quarters were compared with the proposed quarterly estimates. The actual recurrent expenditure for the fourth quarter was N20.001 billion against the proposed estimates of N22.164 billion, representing 90.2% performance level for the quarter while the first quarter performance was 69.6%, second quarter 75.3% and 86.4% for the third quarter.

The fourth quarter estimates for debt repayment stood at N3.400 billion. At the end of the quarter, actual debt repayment figure furnished by the Debt Management Office was N1.545 billion, showing a 45.5% performance level for the quarter while the first quarter performance was 75.9%, second quarter 45.3% and 45.4% for the third quarter.

In similar manner, the proposed estimates for statutory transfer in the fourth quarter of the year was N2.077 billion. At the end of the quarter, actual statutory transfer was N1.625 billion, representing 78.2% performance level for the quarter while the first quarter performance was 36.9%, second quarter 89.3% and 78.2% for the third quarter.

Also, actual capital expenditure was N12.188 billion against the quarterly estimates of N17.716 billion, performing at 68.8% level while the first quarter performance was 15.2%, second quarter 28.4% and 35.9% for the third quarter.

Figure 3.4: Bar Chart Showing Full Year Performance of Expenditure Classifications

Figure 3.4 shows the full year performance of expenditure classifications for the year 2018. The approved estimates for Recurrent Expenditure was N88.654 billion, Debt Repayment N13.600 billion, Statutory Transfer N8.308 billion and N70.863 billion as Capital Expenditure. At the end of the year, Recurrent Expenditure was N71.274 billion, Debt Repayment N7.221 billion, Statutory Transfer N5.872 billion and N26.329 billion as Capital Expenditure, representing 80.4%, 53.0%, 70.17% and 37.2% performance levels respectively for the year.

Figure 3.5: Pie Chart Showing Share of Full Year Actual Expenditure Performance

Figure 3.5 shows that the sum of N110.686 billion was recorded as the actual total expenditure for the year 2018. Specifically, the share of actual Recurrent Expenditure was 64%, actual Debt Repayment 7%, actual Statutory Transfer 5% and 24% as actual Capital Expenditure for the year.

  - RECURRENT EXPENDITURE ANALYSIS

Analysis of recurrent expenditure for the fourth quarter shows that the actual recurrent expenditure for the quarter was N20.001 billion against the proposed estimates of N22.164 billion for the quarter. This figure showed that recurrent expenditure performed at 90.2% level for the quarter while the first quarter performance was 69.6%, second quarter 75.4% and 86.4% for the third quarter.

Table 3.3: Details of Quarterly Recurrent Expenditure Components

| S/N | EXPENDITURE DETAILS | QUARTERLY ESTIMATES N | FIRST QUARTER ACTUAL N | SECOND QUARTER ACTUAL N | THIRD QUARTER ACTUAL N | FOURTH QUARTER ACTUAL N |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | PERSONNEL COST | 10,005,920,769.81 | 7,922,604,467.29 | 8,629,192,940.34 | 8,489,554,539.75 | 8,357,644,680.92 |
| 2 | OVERHEAD COST | 1,125,754,875.00 | 781,682,376.65 | 1,001,709,911.30 | 893,618,741.49 | 819,581,625.67 |
| 3 | SPECIAL PROGRAMME | 4,180,334,489.71 | 2,035,929,337.84 | 2,200,655,856.46 | 3,165,143,100.95 | 4,048,073,172.44 |
| 4 | GRANTS TO PARASTATALS/SUBVENTION | 2,247,609,921.52 | 919,742,037.50 | 1,244,867,337.50 | 2,458,784,584.00 | 2,880,646,154.00 |
| 5 | CONSOLIDATED REVENUE FUND CHARGE | 4,566,417,250.00 | 3,735,999,309.07 | 3,592,314,385.46 | 4,103,021,833.73 | 3,859,278,372.52 |
| 6 | GRANTS/LOANS | 37,500,000.00 | 35,465,600.00 | 26,599,200.00 | 35,465,600.00 | 36,215,600.00 |
|  | TOTAL RECURRENT EXPENDITURE | 22,163,537,306.04 | 15,431,423,128.35 | 16,695,339,631.06 | 19,145,588,399.92 | 20,001,439,605.55 |

SOURCE: Office of Accountant General and other MEDAs, Ondo State

Table 3.3 shows the summary of the recurrent expenditure components for the four quarters of the year 2018. The fourth quarter estimates for Personnel Cost was N10.006 billion, Overhead Cost N1.125 billion, Special Programme N4.180 billion, Grants to Parastatals/Subvention N2.248 billion, Consolidated Revenue Fund Charges N4.566 billion and N0.037 billion as Grants/Loans. At the end of the quarter, the actual of these recurrent expenditure components and performance levels, in the same order were N8.358 billion (83.5%), N0.820 billion (72.8%), N4.048 billion (96.8%), N2.881 billion (128.2%), N3.859 billion (84.5%) and N0.036 billion (96.6%).

Figure 3.6: Bar Chart Showing Quarterly Recurrent Expenditure Components

Table 3.4: Details of Full Year Recurrent Expenditure Components

| S/N | EXPENDITURE DETAILS | APPROVED ESTIMATES N | FULL YEAR ACTUAL N | PERFORMANCE LEVEL (%) |
| --- | --- | --- | --- | --- |
| 1 | PERSONNEL COST | 40,023,683,079.25 | 33,398,996,628.30 | 83.45 |
| 2 | OVERHEAD COST | 4,503,019,500.00 | 3,496,592,655.11 | 77.65 |
| 3 | SPECIAL PROGRAMME | 16,721,337,958.82 | 11,449,801,467.69 | 68.47 |
| 4 | GRANTS TO PARASTATALS/SUBVENTION | 8,990,439,686.07 | 7,504,040,113.00 | 83.47 |
| 5 | CONSOLIDATED REVENUE FUND CHARGE | 18,265,669,000.00 | 15,290,613,900.78 | 83.71 |
| 6 | GRANTS/LOANS | 150,000,000.00 | 133,746,000.00 | 89.16 |
| A | TOTAL RECURRENT EXPENDITURE | 88,654,149,224.14 | 71,273,790,764.88 | 80.40 |

SOURCE: OFFICE OF ACCOUNTANT GENERAL AND OTHER MEDAS,ONDO STATE

Figure 3.7: Bar Chart Showing Full Year Recurrent Expenditure Components

Table 3.4 shows the full year recurrent expenditure components for the year 2018. The approved estimates for Personnel Cost was N40.024 billion, Overhead Cost N4.503 billion, Special Programme N16.721 billion, Grants to Parastatals/Subvention N8.990 billion, Consolidated Revenue Fund Charges N18.266 billion and N0.150 billion as Grants/Loans. At the end of the year, the actual of these recurrent expenditure components and performance levels, in the same order were N33.399 billion (83.5%), N3.497 billion (77.7%), N11.450 billion (68.5%), N7.504 billion (83.5%), N15.290 billion (83.7%) and N0.134 billion (89.2%).

Figure 3.8: Pie Chart Showing Share of Full Year Actual Recurrent Expenditure Components

Figure 3.8 reveals that out of the full year  actual  recurrent expenditure of N71.274 billion, Personnel cost accounted for 47%, Overhead Cost 5%, Special Programme 16%, Grants to Parastatals/Subvention 11%, Consolidated Revenue Fund Charges 21% and Grants/Loans 0.001% for the year 2018.

    - PERSONNEL COST

With approved estimates of N40.024 billion, actual personnel cost for the year was N33.399 billion, representing  83.5% performance level for the year.

Figure 3.9: Bar Chart Showing Full Year Personnel Cost

Table 3.5: Details of Quarterly Personnel Cost

| S/N | PERONNEL DETAILS | SECOND QUARTER ACTUAL | THIRD QUARTER ACTUAL | FOURTH QUARTER ACTUAL |
| --- | --- | --- | --- | --- |
| 1 | CORE CIVIL SERVICE | 4,379,931,120.15 | 4,300,839,175.09 | 4,262,156,651.60 |
| 2 | ADHOC HMB STAFF | 106,543,555.26 | 104,168,989.96 | 109,948,570.44 |
| 3 | ADHOC MIN. OF AGRIC STAFF | 1,697,089.62 | 626,083.42 | 1,571,853.93 |
| 4 | TESCOM (PUB. SECONDARY SCH) | 3,741,154,300.84 | 3,694,056,163.91 | 3,595,962,448.69 |
| 5 | JUDICIAL | 399,866,874.47 | 389,864,127.37 | 388,005,156.26 |
|  | TOTAL | 8,629,192,940.34 | 8,489,554,539.75 | 8,357,644,680.92 |

SOURCE: OFFICE OF ACCOUNTANT GENERAL, ONDO STATE

Table 3.5 shows the personnel cost details for the second, third and fourth quarters of the year 2018. In the classifications of Core Civil Service, Adhoc Hospitals’ Management Board (HMB) Staff, Adhoc Ministry of Agriculture Staff, Teaching Service Commission (TESCOM) Public Secondary School and the Judicial, the actual personnel cost for Core Civil Service for the fourth quarter was N4.262 billion. In similar manner, fourth quarter actual personnel costs for Adhoc HMB Staff, Adhoc Ministry of Agriculture Staff, TESCOM Public Secondary School and the Judicial were N0.109 billion, N0.001 billion, N3.596 billion, and N0.388 billion respectively.

    - OVERHEAD COST

Figure 3.10 compares the approved estimates for overhead cost with the full year actual. With the approved estimates of N4.503 billion, actual overhead cost for the year was N3.497 billion, representing 77.7% performance level for the year.

Figure 3.10: Bar Chart Showing Full Year Overhead Cost

    - SPECIAL PROGRAMMES

The approved estimates for this head was N16.721 billion. At the end of the year, the actual expenditure recorded was N11.450 billion, representing a 68.5% performance level.

Figure 3.11: Bar Chart Showing Full Year Special Programme.

    - SUBVENTIONS/GRANTS TO INSTITUTIONS AND AGENCIES

Table 3.6 shows the full year performance of Subventions/Grants to Institutions and Agencies for the year 2018. The approved estimates for this head was N8.990 billion. At the end of the year, the actual expenditure recorded was N7.504 billion, representing 83.5% performance level.

Table 3.6: Summary of Full Year Subvention/Grants to Parastatals

| S/N | INSTITUTIONS | APPROVED ESTIMATES N | FULL YEAR ACTUAL N | PERFORMANCE LEVEL (%) |
| --- | --- | --- | --- | --- |
| 1 | Adekunle Ajasin University, Akungba Akoko | 1,931,169,686.08 | 2,225,000,000.00 | 115.22 |
| 2 | Nigeria Security and Civil Defence Corps | 2,000,000.00 | 1,510,600.00 | 75.53 |
| 3 | Nigerian Legion | 4,000,000.00 | 3,150,000.00 | 78.75 |
| 4 | Ondo State Agency for Road Maintenance and Construction (OSAMCO) | 50,000,000.00 | 32,663,400.00 | 65.33 |
| 5 | Ondo State Football Academy | 80,000,000.00 |  |  |
| 6 | Ondo State Football Development Agency | 650,000,000.00 | 540,396,091.50 | 83.14 |
| 7 | Ondo State University of Medical Sciences | 600,000,000.00 | 720,000,000.00 | 120.00 |
| 8 | Ondo State University of Science and Technology, Okitipupa | 777,000,000.00 | 695,000,000.00 | 89.45 |
| 9 | Rufus Giwa Polytechnic, Owo | 2,870,000,000.00 | 3,206,521,984.00 | 111.73 |
| 10 | Senior Staff Club | 3,000,000.00 | 2,275,000.00 | 75.83 |
| 11 | Ondo State Investment Promotion Agency (ONDIPA) | 200,000,000.00 | 50,000,000.00 | 25.00 |
| 12 | Ondo State Radiovision Corporation | 50,000,000.00 | 18,448,475.00 | 36.90 |
| 13 | Ondo State Afforestation Project | 10,000,000.00 |  |  |
| 14 | Ondo State Water Corporation | 0.00 | 9,074,562.50 |  |
| 15 | Ondo State University of Medical Sciences Teaching Hospital | 200,000,000.00 |  |  |
| 16 | Provision for Other Grants and Loan | 1,563,270,000.00 |  |  |
|  | TOTAL | 8,990,439,686.08 | 7,504,040,113.00 | 83.47 |

SOURCE: OFFICE OF ACCOUNTANT GENERAL, AND OTHER MEDAS, ONDO STATE

Figure 3.12: Bar Chart Showing Full Year Subvention to Institutions and Agencies

    - CONSOLIDATED REVENUE FUND CHARGES (CFRC)

With approved estimates of N18.266 billion, actual Consolidated Revenue Fund Charges (CRFC) for the year was N15.290 billion, representing 83.7% performance level for the year.

Table 3.7: Details of Full Year Consolidated Revenue Fund Charges (CRFC)

| S/N | EXPENDITURE DETAILS | APPROVED ESTIMATES N | FULL YEAR ACTUAL N | PERFORMANCE LEVEL (%) |
| --- | --- | --- | --- | --- |
| 1 | PENSION | 8,974,403,577.00 | 7,873,366,039.23 | 87.73 |
| 2 | SALARIES OF POLITICAL OFFICE HOLDERS | 859,179,109.00 | 578,128,467.10 | 67.29 |
| 3 | GRATUITY | 2,800,000,000.00 | 3,547,774,842.70 | 126.71 |
| 4 | DIRECT DEDUCTION FROM FAAC (Interest on Short Term Borrowing) | 5,504,891,720.06 | 3,291,344,551.75 | 59.79 |
| 5 | CONTRIBUTORY PENSION (EMPLOYERS) | 102,194,593.00 |  | 0.00 |
| 6 | PAYMENT OF BENEFITS TO PAST GOVERNORS/DEPUTY GOVERNORS | 25,000,000.00 |  | 0.00 |
|  |  | 18,265,668,999.06 | 15,290,613,900.78 | 83.71 |

Source: Office of the Accountant-General/Debt Management Department

Figure 3.13: Bar Chart Showing Full Year Consolidated Revenue Fund Charges (CRFC)

Table 3.7 and Figure 3.13 show the full year CRFC components for the year 2018. The approved estimates for Pension was N8.974 billion, Salaries of Political Office holders N0.859 billion, Gratuity N2.800 billion, Interest component of Direct Deduction from FAAC N5.504 billion, Contributory Pension (Employers) N0.102 billion and Payment of Benefits to Past Governors/Deputy Governors N0.025 billion. At the end of the year, the actuals of the expenditure components, in the same order, were N7.873 billion, N0.578 billion, N3.548 billion, N3.291billion, N0.000 billion and N0.000 billion.

    - GRANTS/LOAN

The approved estimates for Grants/Loan for YR2018 was N150.00 million. At the end of the year, the actual expenditure recorded for this head was N133.746 million, representing 89.2% performance level.

Figure 3.14: Bar Chart Showing Full Year Grants/Loan

  - SECTORAL RECURRENT EXPENDITURE ANALYSIS

Table 3.8 shows the sectoral recurrent expenditure details for the year 2018.

Table 3.8:  Full Year Sectoral Recurrent Expenditure Details

| S/N | Sub-Sector/SECTOR | APPROVED ESTIMATES N | FULL YEAR ACTUAL N | PERFORMANCE LEVEL (%) |
| --- | --- | --- | --- | --- |
| 1 | Agric | 1,590,084,452.01 | 1,287,394,591.32 | 80.96 |
| 2 | Trade & Industry | 621,156,116.50 | 489,149,977.72 | 78.75 |
| 3 | Infrastructure | 2,760,312,473.69 | 1,974,826,400.16 | 71.54 |
| 4 | Public Finance | 8,861,318,838.05 | 8,473,930,601.14 | 95.63 |
| A | TOTAL ECONOMIC SECTOR | 13,832,871,880.25 | 12,225,301,570.34 | 88.38 |
| 1 | Education | 24,880,132,772.90 | 24,116,331,911.73 | 96.93 |
| 2 | Health | 8,268,244,211.65 | 8,542,532,202.34 | 103.32 |
| 3 | Social & Community Development | 2,008,264,261.54 | 1,651,162,714.34 | 82.22 |
| 4 | Environment & Sewage Management | 484,777,571.85 | 476,733,487.67 | 98.34 |
| B | TOTAL SOCIAL SERVICES SECTOR | 35,641,418,817.94 | 34,786,760,316.08 | 97.60 |
| 1 | Administration of Justice | 2,500,775,256.58 | 1,821,617,246.21 | 72.84 |
| C | TOTAL LAW & JUSTICE SECTOR | 2,500,775,256.58 | 1,821,617,246.21 | 72.84 |
| 1 | General Administration | 14,434,339,181.99 | 4,661,718,785.56 | 32.30 |
| 2 | Legislative | 2,901,448,739.07 | 1,806,937,073.64 | 62.28 |
| 3 | Information | 1,077,626,348.31 | 680,841,872.27 | 63.18 |
| D | TOTAL ADMINISTRATION SECTOR | 18,413,414,269.37 | 7,149,497,731.47 | 38.83 |
| E | CONSOLIDATED REVENUE FUND CHARGES | 18,265,669,000.00 | 15,290,613,900.78 | 83.71 |
|  | GRAND TOTAL (A+B+C+D+E) | 88,654,149,224.14 | 71,273,790,764.88 | 80.40 |

Source: Office of the Accountant-General and other MEDAs, Ondo State

The full year sectoral actual recurrent expenditure was N71.273 billion with approved estimates of N88.654 billion. This represents 80.4% overall performance level for the year. In the classifications of Economic sector, Social Services Sector, Law & Justice Sector, Administration Sector and Consolidated Revenue Fund Charges, the Social services sector recorded the highest actual recurrent expenditure of N34.787 billion, representing 97.6% performance level when compared with the approved estimates of N35.641 billion for the year. On the other hand, Administration Sector recorded the least performance at 38.8% level for the year 2018.

Figure 3.15: Bar Chart Showing Full Year Sectoral Recurrent Expenditure

  - STATUTORY TRANSFERS

With approved estimates of N8.308 billion, actual Statutory Transfers to OSOPADEC and Local Governments for the year was N5.872 billion, representing 70.7% performance level for the year.

Table 3.9: Details of Full Year Statutory Transfers

| S/N | PARTICULARS | APPROVED ESTIMATES N | FULL YEAR ACTUAL N | PERFORMANCE LEVEL (%) |
| --- | --- | --- | --- | --- |
| 1 | TRANSFER TO LOCAL GOVERNMENT JOINT ACCOUNT (10%) | 2,093,364,678.30 | 553,272,764.41 | 26.43 |
| 2 | TRANSFER TO OSOPADEC | 6,214,636,800.00 | 5,318,974,573.20 | 85.59 |
|  | TOTAL | 8,308,001,478.30 | 5,872,247,337.61 | 70.68 |

Source: Office of the Accountant-General

Figure 3.16: Bar Chart Showing Full Year Statutory Transfers

  - CAPITAL EXPENDITURE ANALYSIS

The approved estimates for Capital Expenditure for the year was N70.862 billion. At the end of the year, the actual capital expenditure recorded was N26.329 billion, representing 37.2% overall performance level.

Table 3.10:  Full Year Sectoral Capital Expenditure Details

| S/N | Sub-Sector/SECTOR | APPROVED ESTIMATES N | FULL YEAR ACTUAL N | PERFORMANCE LEVEL (%) |
| --- | --- | --- | --- | --- |
| 1 | Agric | 7,459,785,000.00 | 609,423,564.43 | 8.17 |
| 2 | Trade & Industry | 2,305,000,000.00 | 653,243,566.76 | 28.34 |
| 3 | Infrastructure | 24,183,160,000.00 | 14,846,227,411.67 | 61.39 |
| 4 | Public Finance | 2,575,500,000.00 | 348,891,970.69 | 13.55 |
| A | TOTAL ECONOMIC SECTOR | 36,523,445,000.00 | 16,457,786,513.55 | 45.06 |
| 1 | Education | 14,360,512,629.93 | 6,849,886,811.75 | 47.70 |
| 2 | Health | 7,235,734,783.00 | 573,403,472.00 | 7.92 |
| 3 | Social & Community Development | 2,433,000,000.00 | 11,288,726.07 | 0.46 |
| 4 | Environment & Sewage Management | 1,378,000,000.00 | 95,589,146.92 | 6.94 |
| B | TOTAL SOCIAL SERVICES SECTOR | 25,407,247,412.93 | 7,530,168,156.74 | 29.64 |
| 1 | Administration of Justice | 1,457,000,000.00 | 163,730,555.02 | 11.24 |
| C | TOTAL LAW & JUSTICE SECTOR | 1,457,000,000.00 | 163,730,555.02 | 11.24 |
| 1 | General Administration | 6,512,830,083.00 | 2,002,858,417.17 | 30.75 |
| 2 | Legislative | 513,489,000.00 | 27,619,601.89 | 5.38 |
| 3 | Information | 448,500,000.00 | 146,523,991.46 | 32.67 |
| D | TOTAL ADMINISTRATION SECTOR | 7,474,819,083.00 | 2,177,002,010.52 | 29.12 |
|  | GRAND TOTAL (A+B+C+D) | 70,862,511,495.93 | 26,328,687,235.83 | 37.15 |

SOURCE: OFFICE OF ACCOUNTANT GENERAL AND OTHER MEDAs, ONDO STATE

Figure 3.17: Bar Chart Showing Full Year Sectoral Capital Expenditure

Table 3.10 and Figure 3.17 show that the Economic Sector accounted for the highest actual Capital Expenditure of N16.458 billion, representing 45.1% performance level, when compared to the approved estimates of N36.523 billion. On the other hand, Law & Justice Sector, with the least actual expenditure of N0.164 billion recorded 11.2% performance level for the year.

CHAPTER FOUR

STATUS OF CAPITAL PROJECTS AWARDED THROUGH THE STATE TENDER’S BOARD IN 2018

The 2018 Budget tagged “Budget of Progress” was designed to focus on rebuilding the State’s economy through prioritised investment on infrastructural facilities and agriculture-related activities. It was also prepared to strengthen partnership between public and private sector as well as Development Partners to leverage and catalyze resources for growth. In order to achieve the objectives of the cardinal programme of this Administration, a sum of N70.863 billion was budgeted for Capital Expenditure in 2018.

Implementing the 2018 Budget, priorities were given to existing and on-going capital projects. In addition, a total of 709 new capital projects amounting to N48.986 billion were awarded through the State Tenders’ Board (STB) aside other capital projects awarded by MEDAs Ministerial Tenders’ Committee. The total actual payment to the contractors handling new capital projects was N14.908 billion while the overall actual capital expenditure figure for 2018 was N26.329 billion.

4.1	Summary of New Capital Projects Awarded through STB

The summary of new capital projects awarded through STB in 2018 is depicted in table 4.1.

Table 4.1:	Summary of Projects Awarded through STB in 2018

| S/N | MEDAs | NUMBER OF PROJECTS | CONTRACT SUM N | AMOUNT PAID TILL DATE N |
| --- | --- | --- | --- | --- |
| 1 | Ministry of Works and Infrastructure | 19 | 30,846,256,086.22 | 7,909,473,135.53 |
| 2 | Ministry of Information and Orientation | 1 | 8,960,000.00 | 8,960,000.00 |
| 3 | State Universal Basic Education Board SUBEB | 599 | 7,120,524,799.69 | 6,271,057,692.75 |
| 4 | Ondo State Oil Producing Areas Development Commission (OSOPADEC) | 90 | 11,010,621,086.89 | 718,849,155.17 |
|  | TOTAL | 709 | 48,986,361,972.80 | 14,908,339,983.45 |

4.2.	Analysis of MEDAs Implementing New Capital Projects

4.2.1		State Universal Basic Education Board (SUBEB)

The State Universal Basic Education Board (SUBEB) executed 599 projects, amounting to N7.121 billion. At the end of year 2018, a sum of N6.271 billion was actual payment to contractors handling the projects across the eighteen Local Governments in the State .These projects cut across all the eighteen Local Government Areas (LGAs) in the State and were classified into: Construction/Renovation of Block of Classrooms, Construction of Perimeter Fence, Purchase & Supply of ICT Facilities, Purchase and Supply of Play Ground Equipment, Supply and Put in Place Pupils Furniture, Provision of Borehole and Containerised Toilets.

Table 4.2: Status of UBEC/SUBEB Projects

| Level of Project Completion | No of projects | Percentage |
| --- | --- | --- |
| Completed (100%) | 300 | 50.1 |
| Ongoing (1-99%) | 224 | 37.4 |
| Yet to commence (0%) | 75 | 12.5 |
| Total | 599 |  |

Figure 4.1: Bar Chart Showing the Status of the UBEC/SUBEB Projects

Table 4.2 and Figure 4.1 shows that 300 projects representing 50.1 percent of the total projects have been completed in the year under review. 224 projects representing 37.4 percent are ongoing while 75 projects representing 12.5 percent are yet to commence. Those projects that are  yet to commence despite payment of mobilisation fee were majorly Containerised Toilet, Purchase and supply Information facilities (Computer System and other Accessories) and Purchase and Supply of Play Ground Equipment. These projects are subject to the completion of other construction projects.

4.2.2.	Ondo State Oil Producing Areas Development 				Commission (OSOPADEC)

In the year under review, Ondo State Oil Producing Areas Development Commission executed 90 new capital projects which amounted to N11.011 billion out of which N0.719 billion has been paid to contractors as at the end of the year. The projects include the repair/rehabilitation of wooden walkways & Jetties and construction of roads in the areas. The projects were being executed in the oil producing area of the State.

Table 4.3:  Summary of the Projects Executed by OSOPADEC

| S/N | LGAs | NO OF PROJECTS | CONTRACT SUM N | ACTUAL PAYMENT TO CONTRACTORS N |
| --- | --- | --- | --- | --- |
| 1. | ILAJE | 78 | 9,415,098,981.10 | 380,348,288.38 |
| 2. | ESE ODO | 10 | 167,644,308.57 | 47,101,049.04 |
| 3. | AKURE NORTH | 1 | 88,660,830.77 | 20,000,000.00 |
| 4. | OKITIPUPA/IRELE | I | 1,339,216,966.45 | 271,399,817.75 |
|  | TOTAL | 90 | 11,010,621,086.89 | 718,849,155.17 |

Table 4.4: Status of OSOPADEC Projects

| Level of Project Completion | No of projects | Percentage |
| --- | --- | --- |
| Completed (100%) | 3 | 3.3 |
| Ongoing (1-99%) | 86 | 95.6 |
| Yet to commence (0%) | 1 | 1.1 |
| Total | 90 |  |

Table 4.4 shows that 3 of the OSOPADEC projects have been completed, 86 of the projects are ongoing while 1 project is yet to commence. Majority of the ongoing projects are at 60% and above level of completion.

4.2.3.	Ministry of Works and Infrastructure

In 2018, STB awarded 19 new road projects across the State amounting to N30.846 billion, out of which N7.909 billion has been paid to the various contractors. These projects are at various levels of completion. Aside the 19 new road projects, works are also ongoing on projects inherited from the past administration.

CHAPTER FIVE

OBSERVATIONS, RECOMMENDATIONS AND CONCLUSION

5.1	OBSERVATIONS

The following are the observations from the Fourth Quarter/Full Year Budget Implementation Appraisal:

- Overall Budget performance was above average in the year.

- The revenue side of the budget performed at 62.8% for the year.

- Revenue receipts from the Federation Account was N85.380 billion, representing 75% of total revenue for the year.

- Internally Generated Revenue performed at 118.5% for the full year.

- The Full Year total Independent Revenue performance of 118.5% was inclusive of amount generated by the Revenue Retaining Agencies (RRA). Less the RRA, the performance was 92.8%

- The share of Internally Generated Revenue to total actual revenue was 17% for the year.

- Internally Generated Revenue performances on MEDAs basis shows that fourteen MEDAs performed above 100%, nine MEDAs performed between 70% and 99%, four MEDAs performed between 50% and 69% while 34 MEDAs performed below 50%.

- The revenue receipt from Other Sources was abysmally low in the year, performing at 14.4%.

- The expenditure side of the budget performed at 78.0% in the Fourth quarter and 61% for the full year.

- Capital expenditure rose significantly to the tune of N12.188 billion in the fourth quarter, representing 68.8% performance level for the quarter.

- Similarly, capital expenditure recorded a total of N26.328 billion, with 37.2% performance level for the year.

- Recurrent Expenditure recorded a total of N71.274 billion, with 80.4% performance level for the year.

- The total debt repayment made for the year was N7.221 billion, representing 53% performance level.

- Recurrent expenditures accounted for 64% of the total actual expenditures for the full year, debt repayment 7%, Statutory transfers 5% and capital expenditure 24%.

- Late submission of returns by MEDAs is still a challenge causing delay in the timely preparation of the Budget Implementation Appraisal.

5.2	RECOMMENDATIONS

- The performance of the apex revenue generating agency for the year was commendable. However, there is need to consistently improve the State’s Internally Generated Revenue to a level that it will conveniently finance the recurrent expenditure.

- More efforts should be geared towards attracting Development Partners and Donors to the State so as to complement the financing of the various developmental projects in the State.

- Though improving, capital budget implementation should still be given more attention in subsequent years.

- The Monitoring and Evaluation Department of the Ministry of Economic Planning and Budget should be given necessary support to conduct independent monitoring exercise of projects and advise government appropriately.

5.3	CONCLUSION

The overall budget performance in the 2018 Budget Implementation Appraisal was fairly impressive. Both revenue and expenditure performed above sixty percent in the year. While noting the performance, there is still room for more measures to be taken to further improve budget performance in order to reduce budget variance to less than twenty percent in the State.

In conclusion, efforts should be channelled towards addressing the observations and implementing the recommendations in the 2018 Budget Implementation Appraisal for a better budget performance in the subsequent years.

APPENDIX

Table 1: Breakdown of MEDAs Internally Generated Revenue

| S/N | MINISTRIES/DEPTS./PARASTATALS | 2018 TARGET | 2018 ACTUAL | PERFORMANCE |  |
| --- | --- | --- | --- | --- | --- |
| 1 | Ministry of Finance / Accountant General | 766,585,783.00 | 4,974,748,341.74 | 649% |  |
| 2 | State Universal Basic Education Board (SUBEB) | 10,000,000.00 | 42,679,550.00 | 427% |  |
| 3 | Cabinet & Special Services Dept. | 200,000.00 | 813,148.00 | 407% |  |
| 4 | Ondo State Independent Electoral Comm. | 1,000,000.00 | 3,100,000.00 | 310% |  |
| 5 | ONDO STATE INVESTMENT PROMOTION AGENCY (ONDIPA) | 53,000,000.00 | 160,000,000.00 | 302% |  |
| 6 | Hospitals Management Board | 3,500,000.00 | 8,174,800.00 | 234% |  |
| 7 | Christian Welfare Board | 500,000.00 | 932,200.00 | 186% |  |
| 8 | Ondo State Inform. Technology Agency SITA | 30,000,000.00 | 51,382,220.85 | 171% |  |
| 9 | Ministry of Education | 188,451,000.00 | 307,953,181.50 | 163% |  |
| 10 | Teaching Service Commission (TESCOM) | 10,000.00 | 16,200.00 | 162% |  |
| 11 | Customary Court of Appeal | 10,000,000.00 | 14,323,865.19 | 143% |  |
| 12 | Office of Estab. & Services Matter | 500,000.00 | 550,000.00 | 110% |  |
| 13 | Ondo State Liason Office Lagos | 3,000,000.00 | 3,239,597.09 | 108% |  |
| 14 | Pools Betting & Lotteries Board | 25,000,000.00 | 26,902,000.00 | 108% |  |
| 15 | Inter Governmental Affairs & Multilateral Relations | 10,000,000.00 | 9,633,456.00 | 96% |  |
| 16 | Min of Works | 369,400,000.00 | 344,660,382.77 | 93% |  |
| 17 | Office of the State Auditor General | 2,200,000.00 | 1,943,180.98 | 88% |  |
| 18 | Ondo State Pensions Board /Transition dept | 3,500,000.00 | 3,076,050.00 | 88% |  |
| 19 | General Administration Dept. | 1,000,000.00 | 878,740.00 | 88% |  |
| 20 | Board of Internal Revenue (BIR) | 13,650,000,000.00 | 11,719,018,117.97 | 86% |  |
| 21 | The Judiciary | 100,000,000.00 | 80,822,708.00 | 81% |  |
| 22 | Owena Press Limited | 15,000,000.00 | 11,030,347.84 | 74% |  |
| 23 | Ondo State Water Corporation | 11,650,000.00 | 8,362,890.00 | 72% |  |
| 24 | Ondo State Micro Credit Agency | 3,000,000.00 | 2,038,000.00 | 68% |  |
| S/N | MINISTRIES/DEPTS./PARASTATALS | 2018 TARGET | 2018 ACTUAL | PERFORMANCE |  |
| 25 | Min. of Natural Resources | 1,000,000,000.00 | 622,799,728.75 | 62% |  |
| 26 | Min. of Environment | 40,000,000.00 | 22,435,000.00 | 56% |  |
| 27 | Min. of Women Affairs, Youths & Social Deve. | 6,000,000.00 | 3,008,044.43 | 50% |  |
| 28 | Education Endowment Fund | 750,000,000.00 | 353,945,730.62 | 47% |  |
| 29 | Ministry of Culture & Tourism | 16,000,000.00 | 6,099,400.00 | 38% |  |
| 30 | Government House Cabinet & Protocol | 200,000.00 | 75,000.00 | 38% |  |
| 31 | Ondo State Signage Agency | 140,000,000.00 | 51,559,249.67 | 37% |  |
| 32 | Ministry of Inform. Orientation & Mobilisation | 3,000,000.00 | 1,087,000.00 | 36% |  |
| 33 | Ondo State House of Assembly | 2,300,000.00 | 823,000.00 | 36% |  |
| 34 | Min. of Agriculture | 253,250,000.00 | 90,429,405.54 | 36% |  |
| 35 | Government Printing Press | 5,000,000.00 | 1,395,784.82 | 28% |  |
| 36 | Min. of Technical & Vocational Education | 10,000,000.00 | 2,706,404.33 | 27% |  |
| 37 | Min of Physical & URBAN DEV. | 255,000,000.00 | 67,478,731.00 | 26% |  |
| 38 | Agric. Development Program (ADP) | 2,040,000.00 | 531,500.00 | 26% |  |
| 39 | Min. of Local Govt. and Chieftaincy Affairs | 5,500,000.00 | 1,176,000.00 | 21% |  |
| 40 | Min. of Transport | 400,000,000.00 | 74,830,971.04 | 19% |  |
| 41 | Ondo State Devt. & Property Corporation | 950,000,000.00 | 153,317,910.00 | 16% |  |
| 42 | Ministry of Commerce & Industry | 600,000,000.00 | 86,877,275.44 | 14% |  |
| 43 | Land Record Bureau & Housing | 764,000,000.00 | 99,150,181.35 | 13% |  |
| 44 | Ministry of Health | 50,000,000.00 | 5,724,000.00 | 11% |  |
| 45 | Judicial Service Commission | 200,000.00 | 21,050.00 | 11% |  |
| 46 | Ondo State Waste Management Authority | 65,100,000.00 | 6,827,110.00 | 10% |  |
| 47 | Ministry of Justice | 218,600,000.00 | 21,855,307.82 | 10% |  |
| 48 | Cocoa Revolution Office | 94,360,000.00 | 8,031,087.00 | 9% |  |
| 49 | Muslim Welfare Board | 3,500,000.00 | 155,800.00 | 4% |  |
| 50 | Ministry of Regional Intergration & Special Duties | 600,000.00 | 6,500.00 | 1% |  |
| 51 | Accelerated Poverty Alleviation Agency (Former WECA) | 20,000,000.00 | 143,000.00 | 1% |  |
| S/N | MINISTRIES/DEPTS./PARASTATALS | 2018 TARGET | 2018 ACTUAL | PERFORMANCE |  |
| 52 | Ondo State Liason Office Abuja | 2,000,000.00 | 8,000.00 | 0% |  |
| 53 | Agency for Road Maint. and Constr. OSARMCO | 2,400,000.00 | - | 0% |  |
| 54 | Consumer Protection Agency (CPC) | 15,000,000.00 | - | 0% |  |
| 55 | Deputy Governor's Office | 1,000,000.00 | - | 0% |  |
| 56 | Directorate of Rural and Community Development | 780,000.00 | - | 0% |  |
| 57 | ODSACA | 300,000.00 | - | 0% |  |
| 58 | Office of Pulbic Utilities | 2,000,000.00 | - | 0% |  |
| 59 | Office of the Auditor General for Local Govt | 2,520,000.00 | - | 0% |  |
| 60 | Ondo State House of Assembly Service Comm. | 200,000.00 | - | 0% |  |
| 61 | Ondo State Library Board | 300,000.00 | - | 0% |  |
| 62 | Board of Tourism | - | - |  |  |
| 63 | Civic Registration Unit | - | - |  |  |
| 64 | Civil Service Commission |  | 19,000.00 |  |  |
| 65 | Emergency Medical Service Agency | - | - |  |  |
| 66 | Facility Management Department | - | 500.00 |  |  |
| 67 | Fire Services | - | 290,000.00 |  |  |
| 68 | Forestry Staff Training School, Owo |  | 3,246,325.00 |  |  |
| 69 | Local Govt. Service Commission | - | 11,245.00 |  |  |
| 70 | Min. of Comm. Dev & Coop | - | 162,538.00 |  |  |
| 71 | Min. of Economic Planning & Budget |  | 271,220.00 |  |  |
| 72 | Min. of Employment Lab & Productivity | - | 16,000.00 |  |  |
| 73 | Min. of Finance | - | 8,645,602.10 |  |  |
| 74 | Min. of Youths Deve. & Sports |  | 442,625.00 |  |  |
| 75 | NNVS | - | - |  |  |
| 76 | Ondo State Bureau of Statistics | - | - |  |  |
| 77 | Ondo State Boundary Commission | - | - |  |  |
| 78 | Ondo State Library Board | - | 173,000.00 |  |  |
| S/N | MINISTRIES/DEPTS./PARASTATALS | 2018 TARGET | 2018 ACTUAL | PERFORMANCE |
| 79 | Ondo State Scholarship Board | - | 6,000.00 |  |  |
| 80 | Ondo State Task Force on Environm Enforce | - | - |  |  |
| 81 | Projects & Prices Monitorng Unit | - | - |  |  |
| 82 | Special Task Force on Forestry | - | - |  |  |
| 83 | State Pension Commission | - | 11,000.00 |  |  |
| 84 | State Sport Football Agency OSFA | - | - |  |  |
| 85 | State Sports Football Agency (OSFA) | - | 162,000.00 |  |  |
| 86 | WATSAN | - | - |  |  |
| 87 | Ondo State Electricity Board | - | - |  |  |
| 88 | Ondo State Radiovision Corporation | - | - |  |  |
| 89 | AGRI INPUT SUPPLY AGENCY |  | 82,195,000.00 |  |  |
|  | TOTAL | 20,925,646,783.00 | 19,409,010,938.40 | 93 |  |

Table II: Details of MEDAs Recurrent and Capital Expenditure

|  |  |  | RECURRENT EXPENDITURE |  | CAPITAL EXPENDITURE |  |
| --- | --- | --- | --- | --- | --- | --- |
| S/N |  | SECTOR/MDAs/INSTITUTIONS | APPROVED ESTIMATES | FULL YEAR ACTUAL | APPROVED ESTIMATES | FULL YEAR ACTUAL |
| A |  | ECONOMIC SECTOR |  |  |  |  |
| A1 |  | AGRIC SUB SECTOR |  |  |  |  |
| 1 |  | Ministry of Natural Resources | 665,101,017.05 | 569,507,378.16 | 319,500,000.00 | 24,670,850.00 |
| 2 |  | Ondo State Afforestation Project | 10,000,000.00 | - | - | - |
| 3 |  | Ondo State Rural Access and Mobility Project (Community Based Urban Development Project | 8,000,000.00 | 3,600,000.00 | 3,200,000,000.00 | 191,041,955.43 |
| 4 |  | Accelerated Poverty Alleviation Agency (APAA) | 10,080,000.00 | 3,600,000.00 | 430,000,000.00 | 184,765,760.00 |
| 5 |  | Ministry of Agriculture | 516,892,508.12 | 374,612,826.38 | 2,226,800,000.00 | 79,310,999.00 |
| 6 |  | Forestry Training School, Owo | 405,000.00 | 432,852.00 | - | - |
| 7 |  | Agric Development Project | 276,276,656.72 | 250,276,795.60 | 1,043,485,000.00 | 107,330,000.00 |
| 8 |  | Agric Input and Supply Agency | 65,729,270.12 | 66,892,739.18 | 70,000,000.00 | 10,000,000.00 |
| 9 |  | Agroclimatology & Ecological Project | 6,600,000.00 | 3,372,000.00 | 20,000,000.00 | 2,804,000.00 |
| 10 |  | Cocoa Revolution Office | 8,000,000.00 | 3,000,000.00 | 150,000,000.00 | 9,500,000.00 |
| 11 |  | Fadama Project | 9,000,000.00 | 6,100,000.00 | - | - |
| 12 |  | Ondo State UN-REDD+ Project | 14,000,000.00 | 6,000,000.00 | - | - |
|  |  | SUB TOTAL: Agric-sub sector | 1,590,084,452.01 | 1,287,394,591.32 | 7,459,785,000.00 | 609,423,564.43 |
| A2 |  | TRADE AND INDUSTRY SUB SECTOR |  | - | - |  |
| 13 |  | Ministry of Commerce, Industries and Cooperatives | 145,394,776.96 | 182,190,055.70 | 696,000,000.00 | 196,607,450.00 |
| 14 |  | Consumer Protection Committee | 3,670,000.00 | 2,790,650.00 | - | - |
| 15 |  | Micro Credit Agency | 41,804,938.88 | 38,500,333.78 | 10,000,000.00 | 3,129,495.48 |
| 16 |  | Co-operative College, Akure | 324,000.00 | - | - | - |
| 17 |  | Ministry of Employment and Productivity | - | 10,436,410.39 | - | - |
| 18 |  | Ondo State Investment Promotion Agency (ONDIPA) | 200,000,000.00 | 100,000,000.00 | 1,500,000,000.00 | 439,798,700.00 |
|  |  | Free Trade Zone | - | 2,313,849.50 | - | - |
| 19 |  | Ministry of Culture and Tourism | 229,962,400.66 | 145,311,237.71 | 99,000,000.00 | 13,707,921.28 |
|  |  |  | RECURRENT EXPENDITURE |  | CAPITAL EXPENDITURE |  |
| S/N |  | SECTOR/MDAs/INSTITUTIONS | APPROVED ESTIMATES | FULL YEAR ACTUAL | APPROVED ESTIMATES | FULL YEAR ACTUAL |
|  |  | SUB TOTAL: Trade and Industry Sub-Sector | 621,156,116.50 | 489,149,977.72 | 2,305,000,000.00 | 653,243,566.76 |
| A3 |  | INFRASTRUCTURAL SUB SECTOR |  | - | - |  |
| 20 |  | Office of Transport | 445,531,367.56 | 266,757,418.87 | 200,000,000.00 | 12,112,319.48 |
| 21 |  | Office of Transport-Vehicle Inspection (Area) Office and Inland Waterways | 6,980,000.00 | 3,000,000.00 | - | - |
| 22 |  | Ministry of Works and Infrastructure | 435,053,175.39 | 353,038,524.96 | 15,800,000,000.00 | 13,860,452,759.11 |
| 23 |  | Ondo State Agency for Road Maintenance and Construction (OSAMCO) | 50,000,000.00 | 32,663,400.00 | 450,000,000.00 | 19,144,822.00 |
| 24 |  | Ondo State Electricity Board(OSEB) | 662,934,645.04 | 368,546,776.02 | 650,000,000.00 | 361,136.26 |
| 25 |  | Ondo State Water Corporation | 642,863,118.48 | 456,725,862.54 | 4,304,160,000.00 | 2,665,797.10 |
| 26 |  | Ondo State Rural Water Supply and Sanitation Agency (RUWASSA) | 32,866,070.41 | 28,742,598.10 | 305,000,000.00 | 76,430,475.00 |
| 27 |  | Ondo State Development and Property Corporation | 130,783,731.89 | 123,833,667.36 | 314,000,000.00 | - |
| 28 |  | Direct Labour Agency | 9,000,000.00 | 4,200,000.00 | 20,000,000.00 | 7,892,923.25 |
| 29 |  | Ministry of Lands and Housing | 107,731,305.82 | 184,844,950.00 | 1,700,000,000.00 | 790,069,558.35 |
| 30 |  | Ministry of Physical Planning and Urban Development | 186,569,059.10 | 140,246,202.35 | 140,000,000.00 | 66,311,424.52 |
| 31 |  | Office of Public Utilities | 50,000,000.00 | 12,226,999.96 | 300,000,000.00 | 10,786,196.60 |
|  |  | SUB TOTAL: Infrastructure | 2,760,312,473.69 | 1,974,826,400.16 | 24,183,160,000.00 | 14,846,227,411.67 |
| A4 |  | PUBLIC FINANCE SUB SECTOR |  | - | - |  |
| 32 |  | Ondo State Bureau of Statistics | 110,770,803.64 | 56,881,067.69 | 150,000,000.00 | - |
| 33 |  | Board of Internal Revenue | 1,069,253,487.96 | 714,707,751.65 | 90,000,000.00 | 10,130,983.00 |
| 34 |  | Ministry of Economic Planning and Budget | 526,951,016.93 | 339,946,382.68 | 1,223,200,000.00 | 52,776,025.00 |
| 35 |  | Budget Office | 20,000,000.00 | 8,400,000.00 | - | - |
| 36 |  | Manpower Development/MEMIS Project Offices | 10,000,000.00 | 4,250,000.00 | - | - |
| 37 |  | Project and Price Monitoring Unit (PPMU) | 15,000,000.00 | 6,750,000.00 | 85,000,000.00 | 13,935,045.00 |
|  |  |  | RECURRENT EXPENDITURE |  | CAPITAL EXPENDITURE |  |
| S/N |  | SECTOR/MDAs/INSTITUTIONS | APPROVED ESTIMATES | FULL YEAR ACTUAL | APPROVED ESTIMATES | FULL YEAR ACTUAL |
| 38 |  | State Information Technology Agency (SITA) | 126,059,798.83 | 77,296,222.32 | 414,000,000.00 | 75,420,386.12 |
| 39 |  | State Information Technology Agency (SITA) Area Offices | 9,000,000.00 | 24,151,133.05 | - | - |
| 40 |  | Office of the State Auditor General | 412,731,290.79 | 285,598,094.71 | 10,000,000.00 | - |
| 41 |  | Office of Auditor General for Local Government | 77,631,735.91 | 86,956,360.49 | 8,000,000.00 | 3,429,000.00 |
| 42 |  | Pools Bettings and Lotteries Board | 10,000,000.00 | 7,021,000.00 | 34,000,000.00 | - |
| 43 |  | Ministry of Finance | 6,037,075,846.99 | 6,605,928,711.74 | 68,300,000.00 | 19,964,036.42 |
| 44 |  | Expenditure Office | 20,000,000.00 | 31,627,900.00 | - | - |
| 45 |  | Debt Management Office | 18,000,000.00 | 11,770,000.00 | 5,000,000.00 | - |
| 46 |  | Office of the Accountant General | 386,844,857.00 | 207,645,976.81 | 408,000,000.00 | 153,236,495.15 |
| 47 |  | Youth Employment and Social Support Operations (YESSO) | 12,000,000.00 | 5,000,000.00 | 80,000,000.00 | 20,000,000.00 |
|  |  | SUB TOTAL: Public Finance | 8,861,318,838.05 | 8,473,930,601.14 | 2,575,500,000.00 | 348,891,970.69 |
|  |  | TOTAL ECONOMIC SECTOR | 13,832,871,880.25 | 12,225,301,570.34 | 36,523,445,000.00 | 16,457,786,513.55 |
| B |  | SOCIAL SERVICES SECTOR: |  | - | - |  |
| B1 |  | EDUCATION SUB SECTOR |  | - | - |  |
| 48 |  | Zonal Teaching Service Commission, Owena | 3,750,000.00 | 3,000,000.00 | 2,000,000.00 | - |
| 49 |  | Zonal Teaching Service Commission, Owo | 3,750,000.00 | 3,000,000.00 | 2,000,000.00 | - |
| 50 |  | Ondo State Scholarship Board | 63,077,713.73 | 33,330,919.42 | 520,900,000.00 | 3,469,939.00 |
| 51 |  | Board of Adult, Technical and Vocational Education | 612,254,366.82 | 445,939,504.64 | 75,000,000.00 | 4,231,680.00 |
| 52 |  | University Teaching Hospital | - | - | - | - |
| 53 |  | Zonal Teaching Service Commission, Akure | 3,750,000.00 | 3,000,000.00 | 2,000,000.00 | - |
| 54 |  | Zonal Teaching Service Commission, Ikare | 3,750,000.00 | 3,000,000.00 | 2,000,000.00 | - |
| 55 |  | Zonal Teaching Service Commission, Irele | 3,750,000.00 | 3,000,000.00 | 2,000,000.00 | - |
| 56 |  | Zonal Teaching Service Commission, Odigbo | 3,750,000.00 | 3,000,000.00 | 2,000,000.00 | - |
| 57 |  | Zonal Teaching Service Commission, Oka | 3,750,000.00 | 3,000,000.00 | 3,000,000.00 | - |
|  |  |  | RECURRENT EXPENDITURE |  | CAPITAL EXPENDITURE |  |
| S/N |  | SECTOR/MDAs/INSTITUTIONS | APPROVED ESTIMATES | FULL YEAR ACTUAL | APPROVED ESTIMATES | FULL YEAR ACTUAL |
| 58 |  | Zonal Teaching Service Commission, Okitipupa | 3,750,000.00 | 3,000,000.00 | 2,000,000.00 | - |
| 59 |  | Zonal Teaching Service Commission, Ondo | 3,750,000.00 | 3,000,000.00 | 2,000,000.00 | - |
| 60 |  | Ministry of Education, Science and Technology | 1,967,920,890.01 | 1,361,462,839.98 | 1,115,000,000.00 | 158,822,500.00 |
| 61 |  | Zonal Education Offices | 3,750,000.00 | 58,144,404.30 | - | - |
| 62 |  | Ondo State Education Endowment Fund Office | 1,620,000.00 | 2,400,000.00 | - | - |
| 63 |  | State Universal Basic Education Board (SUBEB) Headquarters | 825,718,166.71 | 422,156,065.40 | 9,772,686,368.00 | 6,271,057,692.75 |
| 64 |  | State Universal Basic Education Board (Subeb) Zonal Office | 24,191,200.00 | 6,000,000.00 | - | - |
| 65 |  | Mega Schools | 24,480,000.00 | 37,500,000.00 | - | 505,000.00 |
| 66 |  | Ondo State Library Board | 45,189,101.99 | 38,097,603.06 | 70,000,000.00 | 1,000,000.00 |
| 67 |  | Rufus Giwa polytechnic, Owo | 2,870,000,000.00 | 3,165,556,384.00 | 500,000,000.00 | - |
| 68 |  | Adekunle Ajasin University, Akungba Akoko | 1,931,169,686.07 | 2,225,000,000.00 | 300,000,000.00 | 300,000,000.00 |
| 69 |  | Ondo State University of Science and Technology, Okitipupa | 777,000,000.00 | 695,000,000.00 | 1,200,000,000.00 | 10,000,000.00 |
| 70 |  | Teaching Service Commission | 14,900,011,647.57 | 11,173,459,175.68 | 20,000,000.00 | 800,000.00 |
|  |  | University of Medical Science Teaching Hospital | 200,000,000.00 | - | 267,926,261.93 | - |
| 71 |  | Ondo State University of Medical Sciences | 600,000,000.00 | 720,000,000.00 | 500,000,000.00 | 100,000,000.00 |
|  |  | SUB TOTAL: Education Sub-sector | 24,880,132,772.90 | 24,057,966,845.07 | 14,360,512,629.93 | 6,849,886,811.75 |
| B2 |  | HEALTH SUB SECTOR |  | - | - |  |
| 72 |  | Ondo State Agency for the Control of Aids (ODSACA) | 10,000,000.00 | 4,074,500.00 | 150,000,000.00 | 19,089,600.00 |
| 73 |  | Primary Health Care Management Board | 298,072,456.02 | 346,936,352.03 | 3,598,134,783.00 | 15,000,000.00 |
| 74 |  | Hospital Management Board | 7,142,744,768.63 | 7,573,936,276.17 | 163,000,000.00 | 35,980,000.00 |
| 75 |  | School of Nursing | 2,700,000.00 | 2,100,000.00 | 63,000,000.00 | 3,705,500.00 |
| 76 |  | School of Midwifery | 2,700,000.00 | - | 30,000,000.00 | - |
| 77 |  | School of Health Technology | 2,700,000.00 | 2,700,000.00 | 26,600,000.00 | 1,881,500.00 |
| 78 |  | Emergency Medical Services Agency | 72,000,000.00 | 7,500,000.00 | 50,000,000.00 | 7,770,464.00 |
| 79 |  | Board of Alternative Medicine | 2,328,300.00 | 1,200,000.00 | 2,000,000.00 | - |
| 80 |  | Neuro-Psychiatric Specialist Hospital | 6,763,000.00 | 6,996,000.00 | 5,000,000.00 | - |
| 81 |  | Ministry of Health | 728,235,687.00 | 597,089,074.14 | 3,148,000,000.00 | 489,976,408.00 |
|  |  | SUB TOTAL: Health Sub-Sector | 8,268,244,211.65 | 8,542,532,202.34 | 7,235,734,783.00 | 573,403,472.00 |
|  |  |  | RECURRENT EXPENDITURE |  | CAPITAL EXPENDITURE |  |
| S/N |  | SECTOR/MDAs/INSTITUTIONS | APPROVED ESTIMATES | FULL YEAR ACTUAL | APPROVED ESTIMATES | FULL YEAR ACTUAL |
| B3 |  | SOCIAL AND COMMUNITY DEV. SUB SECTOR |  | - | - |  |
| 82 |  | Ondo State Football Development Agency | 730,000,000.00 | 540,396,091.50 | 110,000,000.00 | - |
| 83 |  | Ministry of Youth and Sports Development | 116,260,031.38 | 91,394,909.81 | 150,000,000.00 | - |
| 84 |  | Ministry of Women Affairs and Social Development | 540,523,132.58 | 694,298,628.48 | 45,000,000.00 | - |
| 85 |  | Agency for the Welfare of the Physically Challenged Persons | 25,400,000.00 | 14,594,200.00 | 5,000,000.00 | 3,096,584.00 |
| 86 |  | Ondo State Sports Council | 376,945,013.82 | 255,791,904.74 | 30,000,000.00 | - |
| 87 |  | Ondo State Football Academy | 80,000,000.00 | - | - | - |
| 88 |  | Ondo State Community and Social Development Agency | 16,600,000.00 | 39,086,979.81 | 590,000,000.00 | - |
| 89 |  | Directorate of Rural and Community Development | 122,536,083.76 | 15,600,000.00 | 1,503,000,000.00 | 8,192,142.07 |
|  |  | SUB TOTAL: Social and Community Dev. Sub-Sector | 2,008,264,261.54 | 1,651,162,714.34 | 2,433,000,000.00 | 11,288,726.07 |
| B4 |  | Environment and Sewage Management Sub-Sector |  | - | - | - |
| 90 |  | Ondo State Waste Management | 293,359,793.96 | 262,113,350.92 | 60,000,000.00 | 30,500,307.00 |
| 91 |  | Ondo State Waste Management Authority Area Office Ondo | - | 11,400,000.00 | - | - |
| 92 |  | Ministry of Environment | 191,417,777.89 | 203,220,136.75 | 1,318,000,000.00 | 65,088,839.92 |
| 93 |  | Environmental Task Force | - | - | - | - |
|  |  | SUB TOTAL: Environment and Sewage Management | 484,777,571.85 | 476,733,487.67 | 1,378,000,000.00 | 95,589,146.92 |
|  |  | TOTAL SOCIAL SERVICES SECTOR: | 35,641,418,817.94 | 34,728,395,249.42 | 25,407,247,412.93 | 7,530,168,156.74 |
| C |  | LAW AND JUSTICE SECTOR |  | - | - |  |
| C1 |  | Administration of Justice |  | - | - |  |
| 94 |  | ONDO STATE JUDICIARY | 1,407,174,534.18 | 1,344,379,765.70 | 1,180,000,000.00 | 74,342,640.84 |
| 95 |  | ONDO STATE JUDICIAL SERVICE COMMISSION | 97,159,752.64 | 42,900,000.00 | 10,000,000.00 | 5,000,000.00 |
| 96 |  | OFFICE OF HONOURABLE CHIEF JUDGE | 30,000,000.00 | 25,100,000.00 | - | - |
| 97 |  | JUDICIARY DIVISION | 20,000,000.00 | 22,500,000.00 | - | - |
| 98 |  | Mobile Court | - | - | - | - |
| 99 |  | MINISTRY OF JUSTICE | 301,972,931.09 | 271,816,869.55 | 222,000,000.00 | 71,427,965.00 |
| 100 |  | ONDO STATE LAW COMMISSION | 23,415,973.68 | 24,573,610.96 | 40,000,000.00 | 10,952,949.18 |
| 101 |  | CITIZEN'S RIGHT MEDIATION CENTRE/OFFICE OF PUBLIC DEFENDERS | 6,264,000.00 | 7,200,000.00 | - | - |
| 102 |  | High Court | - | - | - | - |
| 103 |  | CUSTOMARY COURT OF APPEAL | 580,788,064.99 | 50,009,000.00 | 5,000,000.00 | 957,000.00 |
|  |  |  | RECURRENT EXPENDITURE |  | CAPITAL EXPENDITURE |  |
| S/N |  | SECTOR/MDAs/INSTITUTIONS | APPROVED ESTIMATES | FULL YEAR ACTUAL | APPROVED ESTIMATES | FULL YEAR ACTUAL |
| 104 |  | Customary Court of appeal- judicial divisions | 14,000,000.00 | 14,238,000.00 | - | 1,050,000.00 |
| 105 |  | OFFICE OF THE PRESIDENT OF THE CUSTOMARY COURT OF APPEAL | 20,000,000.00 | 18,900,000.00 | - | - |
|  |  | TOTAL: LAW AND JUSTICE SECTOR | 2,500,775,256.58 | 1,821,617,246.21 | 1,457,000,000.00 | 163,730,555.02 |
| D |  | ADMINISTRATION SECTOR |  | - | - |  |
| D1 |  | General Administration Sub - Sector |  | - | - |  |
| 106 |  | Governor's Office-Government House and Protocol | 2,892,668,304.03 | 2,156,877,791.38 | 240,000,000.00 | 312,325,161.36 |
| 107 |  | Deputy Governor's Office | 520,546,169.65 | 325,987,583.17 | 1,151,000,000.00 | 110,500,000.00 |
| 108 |  | Office of Senior Special Assistants to the Governor | 72,000,000.00 | 123,000,000.00 | - | - |
| 109 |  | Office of the Special Advisers to the Governor | 60,000,000.00 | 3,000,000.00 | - | - |
| 110 |  | Office of A.D.C and C.S.O | - | 4,500,000.00 | - | - |
| 111 |  | Ondo State Boundary Commission | 17,400,000.00 | 11,234,000.00 | 5,000,000.00 | - |
| 112 |  | Nigeria Security and Civil Defence Corps | 2,000,000.00 | 3,310,600.00 | - | - |
| 113 |  | Office of the Head of Service | 48,000,000.00 | 31,200,000.00 | 10,000,000.00 | 837,650.00 |
| 114 |  | Senior Staff Club | 3,000,000.00 | 2,275,000.00 | - | - |
| 115 |  | Public Service Training Institute | 35,200,000.00 | 21,822,150.00 | 80,000,000.00 | 576,500.00 |
| 116 |  | Office of Establishments | 542,061,884.66 | 229,496,325.96 | 15,000,000.00 | 2,286,660.00 |
| 117 |  | Office of the Secretary to State Government (SSG) | 9,504,000.00 | 9,000,000.00 | - | - |
| 118 |  | E-Personel Administration Salary System (e-PASS) Office | 5,550,000.00 | 1,200,000.00 | - | - |
| 119 |  | General Administration | 305,060,784.47 | 248,992,264.73 | 486,000,000.00 | 131,859,321.75 |
| 120 |  | Political and Economic Affairs Department | 1,443,799,242.28 | 808,641,690.83 | - | - |
| 121 |  | State Emergency Management Agency (SEMA) | - | - | 220,000,000.00 | - |
| 122 |  | Cabinet and Special Services Department | 120,313,077.87 | 86,369,424.77 | 5,000,000.00 | 3,267,942.00 |
| 123 |  | Liaison Office, Lagos | 139,256,754.82 | 67,750,945.16 | 10,000,000.00 | - |
| 124 |  | Liaison Office, Abuja | 88,822,677.33 | 47,133,279.92 | 8,000,000.00 | - |
| 125 |  | Service Matters Department | 83,000,000.00 | 23,834,150.00 | 5,000,000.00 | - |
| 126 |  | Ministry of Regional Integration and Special Duties | 92,564,045.36 | 45,721,612.77 | 110,000,000.00 | 27,466,234.00 |
| 127 | Fire Services |  | 5,400,000.00 | - | - | - |
| 128 | Public Complaint Commission/Ombudsman |  | - | - | - | - |
|  |  |  | RECURRENT EXPENDITURE |  | CAPITAL EXPENDITURE |  |
| S/N |  | SECTOR/MDAs/INSTITUTIONS | APPROVED ESTIMATES | FULL YEAR ACTUAL | APPROVED ESTIMATES | FULL YEAR ACTUAL |
| 129 | Ondo State Pensions Transitional Department |  | 46,241,975.30 | 43,269,598.85 | 220,000,000.00 | 10,253,400.00 |
| 130 | Muslim Welfare Board |  | 39,500,000.00 | 35,060,203.00 | 25,000,000.00 | 18,379,211.06 |
| 131 | Christian Welfare Board |  | 55,600,000.00 | 6,936,328.00 | 15,000,000.00 | 3,000,000.00 |
| 132 | Civil Service Commission |  | 128,431,811.07 | 108,946,151.05 | 13,000,000.00 | - |
| 133 | Ondo State Independent Electoral Commission (ODIEC) |  | 74,649,447.71 | 52,307,019.43 | 110,000,000.00 | 30,657,000.00 |
| 134 | Ondo State Independent Electoral Commission (ODIEC) Area Offices |  | 2,000,000.00 | 1,350,000.00 | - | - |
| 135 | Ministry of Local Government and Chieftaincy Affairs |  | 182,671,957.05 | 63,510,929.28 | 12,000,000.00 | - |
| 136 | Local Government Service Commission |  | 4,050,000.00 | 1,800,000.00 | 15,000,000.00 | - |
| 137 | Inter-Governmental Affairs and Multilateral Relations |  | 21,050,000.00 | 5,550,000.00 | 3,732,830,083.00 | 1,351,449,337.00 |
| 138 | Nigerian Legion |  | 4,000,000.00 | 3,150,000.00 | - | - |
| 139 | Consolidated Revenue Fund Charges |  | 18,265,669,000.00 | 15,290,613,900.78 | - | - |
| 140 | Personnel Arrears |  | 5,724,234,835.22 | 55,465,199.84 | - | - |
| 141 | Provision for Other grants and Loans/Personnel Buffer |  | 1,600,113,638.67 | - | - | - |
| 142 | Government Quarters Management Office |  | 3,800,000.00 | 2,400,000.00 | - | - |
| 143 | State Pension Commission |  | 45,848,576.50 | 41,492,137.48 | 25,000,000.00 | - |
| 144 | SA on Youths and Student Affairs |  | - | 3,600,000.00 | - | - |
|  | Industrial and Labour Relation Office/Office of Labour and Union Matters |  | 16,000,000.00 | 5,999,999.94 | - | - |
|  | SA on Multilateral Relations |  | - | - | - | - |
|  | Deputy Chief of Staff |  | - | - | - | - |
|  | SUB TOTAL: General Administration |  | 32,700,008,181.99 | 4,661,718,785.56 | 6,512,830,083.00 | 2,002,858,417.17 |
| D2 | LEGISLATIVE SUB-SECTOR |  |  | - | - |  |
| 145 | State House of Assembly |  | 2,601,195,875.32 | 1,641,978,902.64 | 493,140,000.00 | 27,619,601.89 |
| 146 | House of Assembly Commission |  | 116,752,863.75 | 72,825,171.00 | 20,349,000.00 | - |
| 147 | Offices of the Speaker |  | 96,000,000.00 | 50,400,000.00 | - | - |
|  |  |  | RECURRENT EXPENDITURE |  | CAPITAL EXPENDITURE |  |
| S/N |  | SECTOR/MDAs/INSTITUTIONS | APPROVED ESTIMATES | FULL YEAR ACTUAL | APPROVED ESTIMATES | FULL YEAR ACTUAL |
| 148 | Office of the deputy speaker |  | 79,500,000.00 | 41,733,000.00 | - | - |
| 149 | Public Account secretariat |  | 8,000,000.00 | - | - | - |
|  | SUB TOTAL: Legislative |  | 2,901,448,739.07 | 1,806,937,073.64 | 513,489,000.00 | 27,619,601.89 |
| D3 | INFORMATION SUB-SECTOR |  |  | - | - |  |
| 150 | Ondo State Radiovision Corporation |  | 264,022,075.81 | 163,506,154.69 | 220,000,000.00 | 45,641,400.00 |
| 151 | Ministry of Information and Orientation |  | 555,559,610.50 | 323,564,177.59 | 123,000,000.00 | 72,494,201.66 |
| 152 | Orange FM |  | 78,064,662.00 | 66,124,214.31 | 68,000,000.00 | 25,497,100.00 |
| 153 | Government Printing Press |  | 9,980,000.00 | 1,800,000.00 | 5,000,000.00 | - |
| 154 | Ondo State Signage Agency |  | 20,000,000.00 | 9,834,125.68 | 27,500,000.00 | 2,891,289.80 |
| 155 | Owena Press |  | 150,000,000.00 | 142,612,400.00 | 5,000,000.00 | - |
|  | SUB TOTAL: Information |  | 1,077,626,348.31 | 680,841,872.27 | 448,500,000.00 | 146,523,991.46 |
|  | TOTAL: ADMINISTRATION |  | 36,679,083,269.37 | 7,149,497,731.47 | 7,474,819,083.00 | 2,177,002,010.52 |
|  | GRAND TOTAL |  | 88,654,149,224.14 | 71,273,790,764.88 | 70,862,511,495.93 | 26,328,687,235.83 |