MINISTRY OF ECONOMIC PLANNING AND BUDGET

2022 BUDGET PREPARATION CALENDAR

| S/N | SUBJECT | ACTIVITIES | DATE | RESPONSIBILITY |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | 2021 | Agency | Officer |
| 1. | Commencement of Y2022 Budget Preparation | - Review of Macroeconomic Framework and input of latest data to Multi-Year Budgeting Framework (MYBF) - Preparation and Adoption of Economic and Fiscal Update/Fiscal Strategy Paper (EFU-FSP) 2022 – 2024 - Preparation and Adoption of Budget Policy Statement (BPS) 2022 - Meeting with Major Revenue Generating Agencies on Strategy 2022 – 2024 MTFS - Presentation of 2022 – 2024 MYBF to EXCO - Sectorial Disaggregation of Indicative Envelope - Budget Retreat for MDAs (h) Preparation and refining of MTSS document and compilation of annual budget. | (Beginning) January April-May End May May June June June April-June | MYBF Technical Work Group MYBF Technical Work Group MYBF Technical Work Group MEP&B/ Revenue Stakeholders MEP&B MEP&B MEP&B MEP&B (Director Development Planning) | Director, Budget Director, Budget Director, Budget Director, Budget Honourable Commissioner EXCO Director, Budget Permanent Secretary |
| 2. | 2021 (Current Year) Budget Monitoring & Appraisal | - 1st Quarter 2021 Budget Performance Appraisal - 2nd Quarter / Mid-Year Review of 2021 Budget Performance - 3rd Quarter 2021 Budget Performance Appraisal (d) 4th Quarter/full Year Review of 2021 Budget Performance | 30th April 31st July 31st Oct 31st Jan. 2022 | MEP&B (Director, Monitoring) MEP&B (Director, Monitoring) MEP&B (Director, Monitoring) MEP&B (Director, Monitoring) | Honourable Commissioner Honourable Commissioner Honourable Commissioner Honourable Commissioner |
| 3. | Budget Consultative/ Stakeholders Engagement Process | (a) Meeting with CSOs/NGOs (b) Meeting with Organised Private Sector/ Trade Association/ Professional Bodies (c) Town Hall meetings in 9 Federal Constituencies (d) MTEF Stakeholders Engagement Meeting/Report Dissemination | June June June June | MEP&B (Director Budget) MEP&B (Director Budget) MEP&B (Director Budget) MEP&B (Director Budget) | Permanent Secretary Permanent Secretary Permanent Secretary Permanent Secretary |
| 4. | Preparation of 2022 Budget Estimates | - Issuance of 2022 Call Circular - MDAs Ministerial Budget Defence using MTSS. - Submission of Budget Proposals - Evaluation of Proposals - Pre-Treasury Board Meetings | July Aug Aug Aug Aug | MDAs MEP&B/MDAs MEP&B MEP&B/MDAs MDAs | Permanent Secretaries Permanent Secretaries Permanent Secretaries Director, Budget Permanent Secretaries |
| 5. | 2022 Draft Budget | - Submission of 2022 draft Budget to His Excellency - Treasury Board Meeting - Presentation 2022 Draft Budget to the State Executive Council (d) EXCO/Legislative Parley (e) Presentation of Draft Y2022 Budget Estimates House of Assembly | Sept Sept Sept Sept | Governor’s Office MEP&B MEP&B Mr Governor | Mr. Governor Honourable Commissioner Honourable Commissioner To be agreed with SHoA |
| 6. | Legislative Processes | - Consideration of Budget Proposals by SHoA including interaction with MDAs/scrutiny of estimates. - Passing of the Y2022 Appropriation Bill | Oct 2nd Week Dec | SHoA SHoA |  |
| 7. | Appropriation Law | Printing of the Appropriation Law Assent of Y2022 Budget by the Governor Uploading Approved Budget into the Budget Portal Printing and Publishing of Approved Budget | [Mid] Dec. [end] Dec. [end] Dec. [end] Dec. | SHoA Governor’s Office MEP&B/MDAs MEP&B | Mr Governor Permanent Secretaries Permanent Secretary |
|  |  |  | 2022 |  |  |
| 8. | Execution of 2022 Budget | - Y2022 Budget Analysis - Budget Profiling and Cash Management Plan - Issuance of Budgetary Operation Guidelines | [1st week] Jan. 22 [1st week] Jan. 22 [1st week] Jan. 22 | MEP&B (Budget Dept.) MEP&B/MoF/ MDAs MEP&B (Budget Dept.) | Honourable Commissioner Permanent Secretaries Permanent Secretary |
| 9. | Conclusion of Y2022 Budget | - Y2021 Budget Performance Appraisal for the 4th Quarter/Full Year | 30th Jan. 22 | MEP&B (Director, Monitoring) | Honourable Commissioner |
| 10. | Y2022 Budget Execution Approvals | - Request for approval of implementation of budgeted projects. | On-going in line with cash plan | MDAs | Honourable Commissioner |
| 11. | Disbursement/Fund Release Warrants | - Request for release of funds for approved projects. | On-going in line with cash plan | MDAs/MoF/AG | Permanent Secretaries /DFA |