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MINISTRY OF ECONOMIC PLANNING AND BUDGET
2022 BUDGET PREPARATION CALENDAR

	S/N
	SUBJECT
	ACTIVITIES
	DATE 
	RESPONSIBILITY

	
	
	
	2021
	Agency
	Officer

	1.
	Commencement of Y2022 Budget Preparation
	(a) Review of Macroeconomic Framework and input of latest data to Multi-Year Budgeting Framework (MYBF)

(b) Preparation and Adoption of Economic and Fiscal Update/Fiscal Strategy Paper (EFU-FSP) 2022 – 2024

(c) Preparation and Adoption of Budget Policy Statement (BPS) 2022

(d) Meeting with Major Revenue Generating Agencies on Strategy 2022 – 2024 MTFS

(e) Presentation of 2022 – 2024 MYBF to EXCO

(f) Sectorial Disaggregation of Indicative Envelope

(g) Budget Retreat for MDAs

     (h)   	Preparation and 	refining of MTSS 	document and 	compilation of annual 	budget.
	
(Beginning)
January





April-May 



End
May


May 



June



June 


June



April-June
	MYBF Technical Work Group






MYBF Technical Work Group 



MYBF Technical Work Group 


    MEP&B/
    Revenue        
  Stakeholders


MEP&B



MEP&B


MEP&B


MEP&B (Director Development Planning)

	Director, Budget






Director, Budget



Director, Budget


Director, Budget


Honourable Commissioner 



  EXCO



Director, 
Budget

Permanent Secretary

	2.
	2021 (Current Year) Budget Monitoring & Appraisal
	(a) 1st Quarter 2021 Budget Performance Appraisal

(b) 2nd Quarter / Mid-Year Review of 2021 Budget Performance

(c) 3rd Quarter 2021 Budget Performance Appraisal

 (d)  4th Quarter/full Year                    
       Review of 2021  
       Budget Performance 
	
30th April


31st July


31st Oct


31st Jan. 2022
	MEP&B (Director, Monitoring)

MEP&B (Director, Monitoring)


MEP&B (Director, Monitoring)

MEP&B (Director, Monitoring)
	Honourable Commissioner

Honourable Commissioner


Honourable Commissioner

Honourable Commissioner


	3.
	Budget Consultative/
Stakeholders Engagement Process

	(a)   Meeting with   
       CSOs/NGOs


(b)  Meeting with Organised  
      Private Sector/   
      Trade Association/                
      Professional Bodies


(c)  Town Hall meetings in 9     
       Federal Constituencies 
    
 (d)  MTEF Stakeholders     
       Engagement  
       Meeting/Report           
       Dissemination
	
June

     

     June  



June 



       June

	
MEP&B (Director Budget)


MEP&B (Director Budget)



MEP&B (Director Budget)


MEP&B (Director Budget)

	
Permanent Secretary


Permanent Secretary



Permanent Secretary


Permanent Secretary


	4.
	Preparation of 2022 Budget Estimates
	(a) Issuance of 2022 Call Circular

(b) MDAs Ministerial Budget Defence using MTSS.

(c) Submission of Budget Proposals

(d) Evaluation of Proposals

(e) Pre-Treasury Board Meetings
	July



     Aug 


     Aug 


     Aug 

     Aug
	MDAs




MEP&B/MDAs

MEP&B

MEP&B/MDAs



MDAs
	Permanent Secretaries


Permanent Secretaries

Permanent Secretaries

Director, Budget

Permanent Secretaries

	5.
	2022 Draft Budget
	(a) Submission of 2022 draft Budget to His Excellency
(b) Treasury Board Meeting

(c) Presentation 2022 Draft Budget to the State Executive Council
(d)   EXCO/Legislative Parley
(e) Presentation of Draft Y2022 Budget Estimates House of Assembly
	Sept 



Sept 

Sept 

Sept

	Governor’s Office



MEP&B


MEP&B
Mr Governor
	Mr. Governor



Honourable Commissioner
Honourable Commissioner
To be agreed with SHoA

	6.
	Legislative Processes
	(a) Consideration of Budget Proposals by SHoA including interaction with MDAs/scrutiny of estimates.

(b) Passing of the Y2022 Appropriation Bill
	
Oct 




2nd Week
Dec 
	
SHoA




SHoA

	

	7.
	Appropriation Law
	Printing of the Appropriation Law

Assent of Y2022 Budget by the Governor

Uploading Approved Budget into the Budget Portal


Printing and Publishing of Approved Budget
	[Mid] Dec. 



[end] Dec.


[end] Dec.



[end] Dec.
	SHoA



Governor’s Office


MEP&B/MDAs




MEP&B
	



Mr Governor


Permanent Secretaries


Permanent Secretary

	
	
	
	2022
	
	

	8.
	Execution of 
2022 Budget
	(a) Y2022 Budget Analysis 

(b) Budget Profiling and Cash Management Plan

(c) Issuance of Budgetary Operation Guidelines
	[1st week] Jan. 22 

[1st week] Jan. 22

[1st week] Jan. 22
	MEP&B (Budget Dept.)

MEP&B/MoF/ MDAs

MEP&B (Budget Dept.)
	Honourable Commissioner

Permanent Secretaries

Permanent Secretary

	9.
	Conclusion of Y2022 Budget
	(a) Y2021 Budget Performance Appraisal for the 4th Quarter/Full Year
	
30th Jan. 22
	
MEP&B (Director, Monitoring)
	
Honourable Commissioner

	10.
	Y2022 Budget Execution Approvals 
	Request for approval of implementation of budgeted projects.
	On-going in line with cash plan
	
MDAs
	Honourable Commissioner

	11.
	Disbursement/Fund Release Warrants
	Request for release of funds for approved projects.
	On-going in line with cash plan
	
MDAs/MoF/AG
	Permanent Secretaries /DFA
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